## AVD Plan to 30 Sep
APM Digital Workplace — AVD Program · High-level plan to 30 September 2026
Step / process | Type | Responsible | Depends on | Start | Finish | Status
0 — PROD NETWORK (APM Network Team & Cyber)
Site network build — VLAN 73, Meraki, Palo Alto firewall | Process | APM Network Team | — | 23 Jun | 01 Jul | In progress
Zscaler IPSEC tunnel cutover | Process | APM Cyber | Site network | 25 Jun | 03 Jul | Not started
Azure hub-spoke + AVD spoke build | Process | APM Network Team | — | 23 Jun | 08 Jul | In progress
Network tested end-to-end (AVD FQDNs, Key Vault, Zscaler) | Process | APM Network Team | Azure spoke | 06 Jul | 10 Jul | Not started
Prod network ready & patternised | Milestone | APM Network Team | — | 17 Jul | 17 Jul | Not started
1 — JOB SEEKER KIOSK (P1)
AVD / Nerdio environment + golden image (built & tested) | Process | AVD Build Engineer | — | — | 10 Jul | Complete
Conditional Access + Intune policies + signed scripts | Process | You + AVD Build Eng | — | — | 17 Jul | Complete
Function App + lock-screen password push (to complete) | Process | You | Prod network | TBC | TBC | Blocked
Test device validated (test + prod network) | Milestone | You + AVD Build Eng | Prod network | — | 24 Jul | Not started
Device Build Partner process proven end-to-end | Process | PM + Device Build Partner | Test device | 24 Jul | 04 Aug | Not started
Design update + re-CAB approval | Process | You | Test device | 27 Jul | 31 Jul | Not started
Penetration test + remediation | Process | APM Cyber + You | Design update | 04 Aug | 19 Aug | Not started
Security sign-off — cleared for production | Milestone | APM Cyber | Pen test | 19 Aug | 19 Aug | Not started
National rollout (~517 devices, rolling) | Process | PM | Security sign-off | 21 Aug | 15 Sep | Not started
Job Seeker rollout complete | Milestone | PM | Rollout | 15 Sep | 15 Sep | Not started
2 — STANDARD USER SOE (P2)
DDD finalised + CAB approval | Process | You | DR-010 / DR-011 | 27 Jul | 31 Jul | Not started
AVD build — FSLogix, golden image, Nerdio pool, Intune | Process | AVD Build Engineer | Prod network | 03 Aug | 26 Aug | Not started
Pilot 25–50 users (mixed personas) | Process | You + AVD Build Eng | Build | 26 Aug | 04 Sep | Not started
Design update + penetration test + remediation | Process | You + APM Cyber | Pilot | 04 Sep | 18 Sep | Not started
Production rollout (entitle staff, Windows App self-serve) | Process | APM EUC | Pen test | 18 Sep | 30 Sep | Not started
Standard User AVD GA | Milestone | APM EUC | Rollout | 30 Sep | 30 Sep | Not started
3 — PRIVILEGED ACCESS (P4)
Privileged design (PAW image, tiers zz/xy) + DDD + CAB | Process | You | Prod network | 10 Aug | 28 Aug | Not started
YubiKey 5C NFC FIPS validated | Milestone | AVD Build Eng + APM Cyber | Design | 26 Aug | 26 Aug | Not started
Hardened image + secure pool + PIM build | Process | AVD Build Engineer | DDD approved | 31 Aug | 16 Sep | Not started
Penetration test + remediation | Process | APM Cyber + You | Build | 16 Sep | 28 Sep | Not started
Privileged Access live (zz + xy) | Milestone | You + APM CTO | Pen test | 28 Sep | 28 Sep | Not started
4 — DEVELOPER SOE (P5) — design only by 30 Sep
Developer DDD + landing zone + AIB image pipeline | Process | You + AVD Build Eng | Prod network | 24 Aug | 23 Sep | Not started
Build / pilot / GA fall after 30 Sep (~mid-Oct) | Note | — | — | — | — | Out of window
5 — ES TAKE-HOME — resequenced after Developer
Scheduled after 30 Sep (outside contract window) | Note | — | — | — | — | Out of window