## Summary
APM Digital Workplace — AVD Program Plan
Five AVD use cases on Azure Virtual Desktop via Nerdio · delivered by Twiki Corp for APM
Serialised whole-workstream blocks · Standard User 13 Jul–14 Aug · Privileged 17 Aug–28 Sep · Developer after Priv (GA ~20 Nov) · v1.8
Workstream | Start | End | Tasks | Milestones | Final milestone | Date
0 Network | 23 Jun 2026 | 15 Jul 2026 | 9 | 1 | Network build target | 26 Jun 2026
1 Job Seeker | 24 Jun 2026 | 30 Sep 2026 | 9 | 5 | Phase 2 rollout complete (full ~540 fleet) — subject to device returns | 30 Sep 2026
2 Standard User | 13 Jul 2026 | 14 Aug 2026 | 14 | 3 | Standard User AVD GA | 14 Aug 2026
3 Privileged | 17 Aug 2026 | 28 Sep 2026 | 9 | 3 | Privileged Access live (zz + xy) | 28 Sep 2026
4 Developer | 29 Sep 2026 | 24 Nov 2026 | 12 | 1 | Developer SOE GA (post-contract — ~late Nov) | 20 Nov 2026
5 ES | 27 Jul 2026 | 23 Sep 2026 | 8 | 2 | ES take-home live | 23 Sep 2026
6 Logistics | 13 Jul 2026 | 30 Sep 2026 | 4 | 0 | Retrieve/contract high-priv laptops → users on own Macs (Privileged image) | 30 Sep 2026
7 KB & Enablement | 13 Jul 2026 | 25 Nov 2026 | 8 | 0 | KB: Dev image pipeline/rollback, self-service tooling, MCP request, FSLogix recovery | 25 Nov 2026
TOTALS |  |  | 73 | 15 | 44 critical-path items

## Program Plan
ID | Workstream | Task | Owner (Accountable) | Support (Responsible) | Depends | Start | End | Days | Status | Critical | Dep check
0 Network
N1 | 0 Network | Repurpose JS VLAN → APM-KIOSK (VLAN 73), hidden SSID + PSK via Intune | APM Network Team (IT Infra Mgr) |  | — | 23 Jun 2026 | 26 Jun 2026 | 4 | In progress | Critical | —
N2 | 0 Network | Meraki per-site /26 template, 20Mbps, remove CAPTCHA | APM Network Team (IT Infra Mgr) |  | — | 23 Jun 2026 | 26 Jun 2026 | 4 | In progress | Critical | —
N3 | 0 Network | Palo Alto east-west firewall rules (kiosk→AVD, deny-all) | APM Network Team (IT Infra Mgr) |  | N1 | 24 Jun 2026 | 01 Jul 2026 | 6 | Not started | Critical | Overlap
N4 | 0 Network | Zscaler IPSEC tunnel cutover from ZCC (managed network provider) | APM Cyber | APM Network Team (IT Infra Mgr) | N3 | 25 Jun 2026 | 03 Jul 2026 | 7 | Not started | Critical | Overlap
N5 | 0 Network | MILESTONE: Network build target | APM Network Team (IT Infra Mgr) |  | N1, N2 | 26 Jun 2026 | 26 Jun 2026 | — | Not started | Critical | OK
N6 | 0 Network | Hub VNet — DNS Private Resolver, NAT GW, shared services | APM Network Team (IT Infra Mgr) |  | — | 23 Jun 2026 | 03 Jul 2026 | 9 | In progress | Critical | —
N7 | 0 Network | AVD spoke VNet, NSGs, private endpoints (KV/Files/Func) | APM Network Team (IT Infra Mgr) |  | N6 | 29 Jun 2026 | 08 Jul 2026 | 8 | Not started | Critical | Overlap
N8 | 0 Network | DNS Private Resolver zones + FQDN allowlist validation | APM Network Team (IT Infra Mgr) |  | N7 | 06 Jul 2026 | 10 Jul 2026 | 5 | Not started | — | Overlap
N9 | 0 Network | Test network end-to-end (AVD FQDNs, Key Vault, Zscaler path) | APM Network Team (IT Infra Mgr) | Shaun Struik — build | N4, N7 | 06 Jul 2026 | 10 Jul 2026 | 5 | Not started | Critical | Overlap
N10 | 0 Network | Network design document (final, as-built) | APM Network Team (IT Infra Mgr) |  | N9 | 08 Jul 2026 | 15 Jul 2026 | 6 | Not started | Critical | Overlap
1 Job Seeker
J22 | 1 Job Seeker | Code-signing certificate (D-14) + WDAC allowed-signer rule (D-7) — master gate for device-side pipeline + Nerdio signing | APM Cyber | Shaun Struik — build | — | 24 Jun 2026 | 26 Jun 2026 | 3 | In progress | Critical | —
J1 | 1 Job Seeker | Jobseeker AVD build — golden image (WDAC-hardened) + Nerdio host pool + credential pipeline (Key Vault / Credential Proxy / rotation) + Conditional Access + Shell Launcher + lock-screen credential PR | Shaun Struik — build | Nerdio | N5, J22 | 26 Jun 2026 | 02 Jul 2026 | 6 | In progress | Critical | OK
J6 | 1 Job Seeker | Test AVD build end to end (FVE test env + production network) | Shaun Struik — build | APM Network Team (IT Infra Mgr) | J1 | 02 Jul 2026 | 03 Jul 2026 | 2 | Not started | Critical | OK
J8 | 1 Job Seeker | MILESTONE: Jobseeker AVD build & test complete | Shaun Struik — build | APM Portfolio Mgr | J6 | 03 Jul 2026 | 03 Jul 2026 | — | Not started | Critical | OK
J9 | 1 Job Seeker | Finalise CompNow build instructions + CompNow proves wipe/prep/Autopilot/label/ship | Shaun Struik — build | Device Build Partner | J8 | 06 Jul 2026 | 10 Jul 2026 | 5 | Not started | — | OK
J23 | 1 Job Seeker | User testing (functional + business acceptance) | Nick Dorbie — APM EUC | Ben Riches — APM ES | J8 | 06 Jul 2026 | 10 Jul 2026 | 5 | Not started | Critical | OK
J19 | 1 Job Seeker | Penetration test + remediation (RFFR / ASD ISM scope) | APM Cyber | Shaun Struik — build | J8 | 03 Jul 2026 | 10 Jul 2026 | 6 | Not started | Critical | OK
J21 | 1 Job Seeker | MILESTONE: User testing + security sign-off complete — cleared for rollout | Nick Dorbie — APM EUC | APM CTO/CISO | J23, J19 | 10 Jul 2026 | 10 Jul 2026 | — | Not started | Critical | OK
J13 | 1 Job Seeker | Roll out to pilot + priority sites | Twiki team | Ben Riches — APM ES | J21, J9 | 13 Jul 2026 | 31 Jul 2026 | 15 | Not started | Critical | OK
J12 | 1 Job Seeker | MILESTONE: Pilot + priority sites complete | Twiki PM | APM Portfolio Mgr | J13 | 31 Jul 2026 | 31 Jul 2026 | — | Not started | Critical | OK
J16 | 1 Job Seeker | Phase 1 rollout — new devices (~360 of 540), rolling | Twiki PM | Device Build Partner | J12 | 04 Aug 2026 | 31 Aug 2026 | 20 | Not started | Critical | OK
J17 | 1 Job Seeker | MILESTONE: Phase 1 rollout complete (~360 of 540 devices) | Twiki PM | Ben Riches — APM ES | J16 | 31 Aug 2026 | 31 Aug 2026 | — | Not started | Critical | OK
J24 | 1 Job Seeker | Phase 2 rollout — remaining ~180 devices (reimaged returns). DEPENDS ON return of old devices; pace/scope conditional on returned-device condition — faulty / out-of-warranty units need replacement (CompNow + SoftwareOne), not reimage | Twiki PM | Device Build Partner | J17, L1 | 01 Sep 2026 | 30 Sep 2026 | 22 | Not started | — | OK
J25 | 1 Job Seeker | MILESTONE: Phase 2 rollout complete (full ~540 fleet) — subject to device returns | Twiki PM | Ben Riches — APM ES | J24 | 30 Sep 2026 | 30 Sep 2026 | — | Not started | — | OK
2 Standard User
S1 | 2 Standard User | Document current Intune laptop SOE + Autopilot (14 policies) | Shaun Struik — build | Nick Dorbie — APM EUC | — | 13 Jul 2026 | 16 Jul 2026 | 4 | Not started | — | —
S2 | 2 Standard User | Close DR-010 printing + DR-011 mapped drive decisions | APM Head Digital Ops | Shaun Struik — build | — | 13 Jul 2026 | 16 Jul 2026 | 4 | Not started | — | —
S3 | 2 Standard User | Finalise DDD V1.0 + CAB | Shaun Struik — build | APM Head Arch. | S1, S2 | 16 Jul 2026 | 20 Jul 2026 | 3 | Not started | — | OK
S4 | 2 Standard User | MILESTONE: Standard User DDD approved | APM Head Arch. | APM Portfolio Mgr | S3 | 20 Jul 2026 | 20 Jul 2026 | — | Not started | — | OK
S5 | 2 Standard User | Entra groups (corp/BYOD/hosts) + CA (block unmanaged, allow Windows App) | Shaun Struik — build | APM Cyber | S4 | 20 Jul 2026 | 24 Jul 2026 | 4 | Not started | — | OK
S6 | 2 Standard User | Azure Files Premium FSLogix + Entra Kerberos | AVD Build Engineer | Shaun Struik — Architect / Design | N7, S4 | 20 Jul 2026 | 24 Jul 2026 | 4 | Not started | — | OK
S7 | 2 Standard User | Compute Gallery + golden image (multi-session, M365, Teams optimised) | AVD Build Engineer | Nick Dorbie — APM EUC | S6 | 24 Jul 2026 | 30 Jul 2026 | 5 | Not started | — | OK
S8 | 2 Standard User | Nerdio pooled host pool + corp/BYOD app groups + autoscale | AVD Build Engineer | Nerdio | S7 | 30 Jul 2026 | 02 Aug 2026 | 3 | Not started | — | OK
S9 | 2 Standard User | Scope 14 Intune policies + AVD profiles to session hosts | AVD Build Engineer | Nick Dorbie — APM EUC | S7 | 30 Jul 2026 | 02 Aug 2026 | 3 | Not started | — | OK
S17 | 2 Standard User | MILESTONE: Standard User image build complete | AVD Build Engineer | APM Portfolio Mgr | S8, S9 | 02 Aug 2026 | 02 Aug 2026 | — | Not started | Critical | OK
S10 | 2 Standard User | Pilot 25–50 users (mixed personas) | Shaun Struik — build | Nick Dorbie — APM EUC | S17 | 02 Aug 2026 | 07 Aug 2026 | 5 | Not started | — | OK
S14 | 2 Standard User | Update DDD with as-built changes + re-CAB approval | Shaun Struik — build | APM Head Arch. | S17 | 02 Aug 2026 | 04 Aug 2026 | 2 | Not started | — | OK
S15 | 2 Standard User | Penetration test (Standard User SOE) | APM Cyber | Shaun Struik — build | S14 | 04 Aug 2026 | 08 Aug 2026 | 4 | Not started | Critical | OK
S11 | 2 Standard User | Validate CA from corporate + personal device | Shaun Struik — build | APM Cyber | S5, S10 | 07 Aug 2026 | 09 Aug 2026 | 2 | Not started | — | OK
S16 | 2 Standard User | Remediate pen-test findings + retest | AVD Build Engineer | APM Cyber | S15 | 08 Aug 2026 | 11 Aug 2026 | 3 | Not started | Critical | OK
S12 | 2 Standard User | Production rollout (entitle staff, comms, Windows App self-serve) | Nick Dorbie — APM EUC | APM Digital Business Partner | S11, S16 | 11 Aug 2026 | 14 Aug 2026 | 3 | Not started | — | OK
S13 | 2 Standard User | MILESTONE: Standard User AVD GA | Nick Dorbie — APM EUC | APM Portfolio Mgr | S12 | 14 Aug 2026 | 14 Aug 2026 | — | Not started | Critical | OK
3 Privileged
P1 | 3 Privileged | Privileged design: PAW-style hardened image (no mail/Teams/browse), tiers Priv(zz)/High-Priv(xy) | Shaun Struik — build | APM Cyber | N10 | 17 Aug 2026 | 26 Aug 2026 | 8 | Not started | — | OK
P2 | 3 Privileged | Production access model: PIM per tier, JIT elevation, approval + audit | Shaun Struik — build | APM Cyber | P1 | 21 Aug 2026 | 28 Aug 2026 | 6 | Not started | — | Overlap
P3 | 3 Privileged | Privileged Access DDD + CAB | Shaun Struik — build | APM Head Arch. | P2 | 27 Aug 2026 | 01 Sep 2026 | 4 | Not started | — | Overlap
P4 | 3 Privileged | MILESTONE: Privileged DDD approved | APM Head Arch. | APM CTO/CISO | P3 | 01 Sep 2026 | 01 Sep 2026 | — | Not started | — | OK
P5 | 3 Privileged | Test YubiKey 5C NFC FIPS (phishing-resistant MFA for zz/xy) | AVD Build Engineer | APM Cyber | P1 | 21 Aug 2026 | 28 Aug 2026 | 6 | Not started | Critical | Overlap
P6 | 3 Privileged | MILESTONE: YubiKey 5C NFC FIPS validated | APM Cyber | Shaun Struik — build | P5 | 28 Aug 2026 | 28 Aug 2026 | — | Not started | Critical | OK
P7 | 3 Privileged | Build hardened Privileged image + secure pool | AVD Build Engineer | Shaun Struik — Architect / Design | P4 | 01 Sep 2026 | 10 Sep 2026 | 8 | Not started | Critical | OK
P8 | 3 Privileged | CA + PIM for Priv(zz) & High-Priv(xy) prod scopes; YubiKey-only sign-in | Shaun Struik — build | APM Cyber | P6, P7 | 10 Sep 2026 | 16 Sep 2026 | 6 | Not started | Critical | OK
P9 | 3 Privileged | Pilot privileged users (both tiers) + validate prod access via YubiKey | Shaun Struik — build | APM Cyber | P8 | 16 Sep 2026 | 22 Sep 2026 | 5 | Not started | — | OK
P11 | 3 Privileged | Penetration test (Privileged image — PAW hardening, prod-access boundary) | APM Cyber | Shaun Struik — build | P8 | 16 Sep 2026 | 22 Sep 2026 | 5 | Not started | Critical | OK
P12 | 3 Privileged | Remediate pen-test findings + retest | AVD Build Engineer | APM Cyber | P11, P9 | 22 Sep 2026 | 28 Sep 2026 | 4 | Not started | Critical | OK
P10 | 3 Privileged | MILESTONE: Privileged Access live (zz + xy) | Shaun Struik — build | APM CTO/CISO | P12 | 28 Sep 2026 | 28 Sep 2026 | — | Not started | Critical | OK
4 Developer
D1 | 4 Developer | Finalise Dev DDD: permissive dev image, limited blocks, no production path — Developer work commences after Privileged completes | Shaun Struik — build | APM Head Arch. | N10, P10 | 29 Sep 2026 | 07 Oct 2026 | 7 | Not started | — | OK
D2 | 4 Developer | Design Dev network from JS pattern + adjust (deny-by-default egress, Zscaler at endpoint) | Shaun Struik — build | APM Network Team (IT Infra Mgr) | N10, P10 | 05 Oct 2026 | 09 Oct 2026 | 5 | Not started | — | OK
D3 | 4 Developer | AVD landing zone (Bicep) + FSLogix Premium ZRS + Sentinel + Entra groups | AVD Build Engineer | Shaun Struik — Architect / Design | D1, D2 | 09 Oct 2026 | 16 Oct 2026 | 6 | Not started | Critical | OK
D4 | 4 Developer | AIB image pipeline (Git template, signing, SBOM) | AVD Build Engineer | APM Cyber | D3 | 16 Oct 2026 | 22 Oct 2026 | 5 | Not started | Critical | OK
D5 | 4 Developer | Primary pooled host pool + scaling plan (nested virtualisation) | AVD Build Engineer | Nerdio | D4 | 22 Oct 2026 | 28 Oct 2026 | 4 | Not started | Critical | OK
D6 | 4 Developer | Dev tooling layers (VS, Podman/containers, WSL2) with limited blocks | AVD Build Engineer | Nick Dorbie — APM EUC | D5 | 28 Oct 2026 | 03 Nov 2026 | 5 | Not started | Critical | OK
D7 | 4 Developer | Pilot ring (PDE owner + cohort) + smoke test + CA enforced | Shaun Struik — build | APM PDE Owner (TBC) | D5, D6 | 03 Nov 2026 | 09 Nov 2026 | 5 | Not started | — | OK
D12 | 4 Developer | Penetration test (Developer SOE — permissive image, no-prod-path boundary) | APM Cyber | Shaun Struik — build | D6 | 03 Nov 2026 | 10 Nov 2026 | 6 | Not started | Critical | OK
D13 | 4 Developer | Remediate pen-test findings + retest | AVD Build Engineer | APM Cyber | D12 | 10 Nov 2026 | 16 Nov 2026 | 4 | Not started | Critical | OK
D9 | 4 Developer | Capability phase 2 enabled at GA (winget/ACR); phase 3 (Copilot/MCP/local LLM) configured | AVD Build Engineer | APM Cyber | D7 | 09 Nov 2026 | 16 Nov 2026 | 6 | Not started | — | OK
D8 | 4 Developer | Team-by-team migration from legacy PDE | AVD Build Engineer | Nick Dorbie — APM EUC | D7, D13 | 16 Nov 2026 | 20 Nov 2026 | 4 | Not started | Critical | OK
D10 | 4 Developer | Begin legacy PDE decommission (cutover; full retire after stability window) | AVD Build Engineer | APM Head Digital Ops | D8 | 20 Nov 2026 | 24 Nov 2026 | 2 | Not started | — | OK
D11 | 4 Developer | MILESTONE: Developer SOE GA (post-contract — ~late Nov) | Shaun Struik — build | APM Portfolio Mgr | D8, D13 | 20 Nov 2026 | 20 Nov 2026 | — | Not started | Critical | OK
5 ES
E1 | 5 ES | Adapt JS image: midnight daily reset (vs 10-min inactivity) | AVD Build Engineer | Ben Riches — APM ES | J8 | 27 Jul 2026 | 31 Jul 2026 | 5 | Not started | — | OK
E2 | 5 ES | Redesign take-home: any Wi-Fi, off-site filtering (Zscaler on device), revised CA | Shaun Struik — build | APM Cyber | E1 | 03 Aug 2026 | 14 Aug 2026 | 10 | Not started | Critical | OK
E3 | 5 ES | ES DDD + CAB | Shaun Struik — build | APM Head Arch. | E2 | 17 Aug 2026 | 21 Aug 2026 | 5 | Not started | — | OK
E4 | 5 ES | MILESTONE: ES DDD approved | APM Head Arch. | APM Portfolio Mgr | E3 | 21 Aug 2026 | 21 Aug 2026 | — | Not started | — | OK
E5 | 5 ES | Build ES image/profiles (midnight reset, incl. Eskilled folder) | AVD Build Engineer | APM ES Training Owner | E4 | 24 Aug 2026 | 02 Sep 2026 | 8 | Not started | — | OK
E6 | 5 ES | Test off-site scenarios (home Wi-Fi, reset, filtering) | Twiki team | Ben Riches — APM ES | E5 | 02 Sep 2026 | 07 Sep 2026 | 4 | Not started | Critical | OK
E9 | 5 ES | Penetration test (ES take-home — off-site filtering, midnight reset, CA) | APM Cyber | Shaun Struik — build | E5 | 02 Sep 2026 | 09 Sep 2026 | 5 | Not started | Critical | OK
E10 | 5 ES | Remediate pen-test findings + retest | AVD Build Engineer | APM Cyber | E9, E6 | 09 Sep 2026 | 15 Sep 2026 | 4 | Not started | Critical | OK
E7 | 5 ES | Pilot + rollout (take-home devices) | Twiki PM | Ben Riches — APM ES | E6, E10 | 15 Sep 2026 | 23 Sep 2026 | 6 | Not started | — | OK
E8 | 5 ES | MILESTONE: ES take-home live | Twiki PM | APM Portfolio Mgr | E7 | 23 Sep 2026 | 23 Sep 2026 | — | Not started | Critical | OK
6 Logistics
L1 | 6 Logistics | Retrieve old JS devices onsite + place new (rolling) | Twiki PM | Ben Riches — APM ES | J8 | 13 Jul 2026 | 21 Aug 2026 | 29 | Not started | — | OK
L2 | 6 Logistics | Asset register updates (ongoing) | Twiki PM | Nick Dorbie — APM EUC | — | 04 Aug 2026 | 30 Sep 2026 | 42 | Not started | — | —
L3 | 6 Logistics | Retrieve standard-user laptops as AVD replaces | Twiki PM | Nick Dorbie — APM EUC | S13 | 07 Sep 2026 | 30 Sep 2026 | 18 | Not started | — | OK
L4 | 6 Logistics | Retrieve/contract high-priv laptops → users on own Macs (Privileged image) | Twiki PM | APM Portfolio Mgr | P10 | 23 Sep 2026 | 30 Sep 2026 | 6 | Not started | — | Overlap
7 KB & Enablement
K1 | 7 KB & Enablement | KB: APM-KIOSK network build | Shaun Struik — build | APM Digital Business Partner | N10 | 13 Jul 2026 | 20 Jul 2026 | 6 | Not started | — | Overlap
K2 | 7 KB & Enablement | KB: Device Build Partner wipe/prep/ship process | Shaun Struik — build | APM Digital Business Partner | J9 | 24 Jul 2026 | 29 Jul 2026 | 4 | Not started | — | OK
K3 | 7 KB & Enablement | KB: JS ops (password rotation, lock screen, device replace) | Shaun Struik — build | APM Digital Business Partner | J8 | 27 Jul 2026 | 10 Aug 2026 | 11 | Not started | — | OK
K4 | 7 KB & Enablement | KB: image/patch, FSLogix lifecycle, CA BYOD, Windows App onboarding | Shaun Struik — build | APM Digital Business Partner | S8 | 26 Aug 2026 | 07 Sep 2026 | 9 | Not started | — | OK
K5 | 7 KB & Enablement | KB: ES midnight reset, off-site connectivity, Eskilled access | Shaun Struik — build | APM Digital Business Partner | E5 | 02 Sep 2026 | 10 Sep 2026 | 8 | Not started | — | OK
K6 | 7 KB & Enablement | KB: Privileged access request, PIM per tier (zz/xy), YubiKey enrolment | Shaun Struik — build | APM Digital Business Partner | P7 | 09 Sep 2026 | 18 Sep 2026 | 8 | Not started | — | Overlap
K7 | 7 KB & Enablement | KB: Dev image pipeline/rollback, self-service tooling, MCP request, FSLogix recovery | Shaun Struik — build | APM Digital Business Partner | D6 | 17 Nov 2026 | 25 Nov 2026 | 7 | Not started | — | OK
K8 | 7 KB & Enablement | KB: Tier-1 Service Desk triage runbooks (all use cases) | Shaun Struik — build | APM Digital Business Partner | K3 | 14 Sep 2026 | 30 Sep 2026 | 13 | Not started | — | OK

## Milestones
ID | Milestone | Workstream | Date | Critical
N5 | Network build target | 0 Network | 26 Jun 2026 | Critical
J8 | Jobseeker AVD build & test complete | 1 Job Seeker | 03 Jul 2026 | Critical
J21 | User testing + security sign-off complete — cleared for rollout | 1 Job Seeker | 10 Jul 2026 | Critical
S4 | Standard User DDD approved | 2 Standard User | 20 Jul 2026 | —
J12 | Pilot + priority sites complete | 1 Job Seeker | 31 Jul 2026 | Critical
S17 | Standard User image build complete | 2 Standard User | 02 Aug 2026 | Critical
S13 | Standard User AVD GA | 2 Standard User | 14 Aug 2026 | Critical
E4 | ES DDD approved | 5 ES | 21 Aug 2026 | —
P6 | YubiKey 5C NFC FIPS validated | 3 Privileged | 28 Aug 2026 | Critical
J17 | Phase 1 rollout complete (~360 of 540 devices) | 1 Job Seeker | 31 Aug 2026 | Critical
P4 | Privileged DDD approved | 3 Privileged | 01 Sep 2026 | —
E8 | ES take-home live | 5 ES | 23 Sep 2026 | Critical
P10 | Privileged Access live (zz + xy) | 3 Privileged | 28 Sep 2026 | Critical
J25 | Phase 2 rollout complete (full ~540 fleet) — subject to device returns | 1 Job Seeker | 30 Sep 2026 | —
D11 | Developer SOE GA (post-contract — ~late Nov) | 4 Developer | 20 Nov 2026 | Critical

## Risks & Open Decisions
# | Risk / Assumption / Open decision | Impact | Likelihood | Owner | Mitigation / Recommendation
1 | APM is running several tier-one projects at once. The AVD schedule depends on APM departments (Network, Cyber, EUC) and decision-makers delivering their inputs on time; contention for APM resources and approvals — not delivery capacity — is the main risk to the 30 Sep dates. | High | High | Portfolio Mgr (APM) | Lock an APM owner and due date for every dependency (network, DR-010/011, pen-test window, PDE owner). Weekly dependency review with the Portfolio Manager; escalate APM-side slippage immediately.
2 | Network (site + Azure) is on the critical path from day one and is delivered by APM Network / Infrastructure. APM-side network slippage directly delays Job Seeker testing and rollout. | High | Med | Network Lead / Architect | Confirm APM Network resourcing now; daily stand-up until network proven. Twiki supports the Azure foundation.
3 | Privileged Access is net-new (PAW, two tiers, YubiKey) added mid-window; carries production blast-radius risk. | High | Med | Cyber lead (Ugbaad Adani) | Design once, gate hard on YubiKey; the Cyber lead signs off the privileged model; no high-priv cutover until P6 + P8 pass.
4 | YubiKey 5C NFC FIPS gates Privileged production access; if it fails, no phishing-resistant path from Macs. | High | Med | Shaun Struik / Cyber | Run YubiKey test early (wk 17 Aug). Fallback to a dedicated hardened Cloud PC for the highest tier.
5 | ES take-home breaks the site-VLAN / PSK / site-Zscaler controls JS relies on — a security redesign. Now compressed into Aug–Sep to land by 30 Sep, running in parallel with Standard User, Privileged and Developer builds. | High | High | Shaun Struik / Cyber | Treat ES as its own design (Zscaler client on device, revised CA, any Wi-Fi, midnight reset). Confirm Eskilled path early; protect the Aug–Sep build capacity.
6 | Developer must stay a permissive image with no production path; production access lives only in the Privileged image. | Med | Low | Shaun Struik / Head Arch. | Keep the boundary clean — no production scopes on the Dev pool.
7 | Standard User printing (DR-010) and mapped drive (DR-011) still pending; both gate the SU build. | Med | High | Head Digital Ops / EUC | Force decisions by 24 Jul. Universal Print likely; confirm mapped-drive backend.
8 | RESOLVED — Job Seeker device count confirmed at 540 (early drafts showed 517 vs 540). | Low | Low | Twiki PM / EUC | Done — 540 is the confirmed count, applied everywhere.
9 | RESOLVED — Nerdio environment is set up and complete; Standard User, Privileged, Developer and ES all reuse it. | Low | Low | Shaun Struik / Architect | Done. No action.
10 | Developer (PDE) owner not yet named — gates Dev pilot, image approval and service catalogue. | Med | Med | Portfolio Mgr / Head Digital Ops | Nominate the APM PDE owner now.
11 | A single AVD Build Engineer cannot build images in parallel, so the use cases are serialised whole-workstream blocks: Standard User (full lifecycle design→GA, 13 Jul–14 Aug) → Privileged (17 Aug–28 Sep) → Developer (commences immediately after Privileged, runs to ~20 Nov). Two consequences: (a) the Standard User window is very tight — image complete ~2 Aug then pilot, pen-test, remediation and production rollout all inside ~12 days; (b) Developer cannot start until 29 Sep and lands ~20 Nov, PAST the 30 Sep contract end. Network, Job Seeker, Standard User, ES and Privileged all complete by 30 Sep. | High | High | Portfolio Mgr | For Standard User, pre-book the pen-test window and agree a fast retest turnaround, or accept a staged rollout where GA is “pilot-proven + pen-test booked”. For Developer, confirm APM accepts post-contract GA, or add a second build engineer from mid-Aug to run Privileged and Developer in parallel. Hold every APM dependency (network, DR-010/011, pen-test windows, PDE owner) to a confirmed date.
12 | Every image now requires a penetration test + remediation before go-live (RFFR / ASD ISM). No pen-test vendor or booked window is confirmed — an external scheduling dependency that gates every go-live. | High | High | Shaun Struik / Cyber / Portfolio Mgr | Book the pen-test vendor now and reserve per-image windows. Bundle Job Seeker + Standard User into one engagement; confirm scope and retest turnaround up front.