## Program Plan
APM Digital Workplace — AVD Program Plan & Gantt
ID | Workstream | Phase | Task | Owner (Accountable) | Support (Responsible) | Depends | Start | End | Days | % | Status
0 Network
N1 ▲ | 0 Network | Site network | Repurpose JS VLAN to APM-KIOSK (VLAN 73), hidden SSID + PSK via Intune | APM Network - Michael Court | Twiki - Shaun Struik | — | 23 June | 26 June | 4 | 0 | In progress
N2 ▲ | 0 Network | Site network | Meraki per-site /26 template, 20Mbps, remove CAPTCHA | APM Network - Michael Court | Twiki - Michael Webster | — | 23 June | 26 June | 3 | 0 | In progress
N3 ▲ | 0 Network | Site network | Palo Alto east-west firewall rules (kiosk to AVD, deny-all) | APM Network - Michael Court | APM Cyber - Ugbaad Adani | N1 | 24 June | 01 July | 7 | 0 | Not started
N4 ▲ | 0 Network | Site network | Zscaler IPSEC tunnel (Stratus) cutover from ZCC | APM Network - Michael Court | APM Cyber - Ugbaad Adani | N3 | 25 June | 03 July | 8 | 0 | Not started
N5 ▲ | 0 Network | Site network | MILESTONE: Network build target | APM Network - Michael Court | Twiki - Shaun Struik | N1, N2 | 26 June | 26 June |  |  | Not started
N6 ▲ | 0 Network | Azure foundation | Hub VNet - DNS Private Resolver, NAT GW, shared services | Twiki - Michael Webster | Twiki - Shaun Struik | — | 23 June | 03 July | 10 | 0 | In progress
N7 ▲ | 0 Network | Azure foundation | AVD spoke VNet, NSGs, private endpoints (KV/Files/Func) | Twiki - Shaun Struik | Twiki - Michael Webster | N6 | 29 June | 08 July | 9 | 0 | Not started
N8 | 0 Network | Azure foundation | DNS Private Resolver zones + FQDN allowlist validation | Twiki - Shaun Struik | APM Network - Michael Court | N7 | 06 July | 10 July | 4 | 0 | Not started
N9 ▲ | 0 Network | Test & document | Test network end-to-end (AVD FQDNs, Key Vault, Zscaler path) | Twiki - Shaun Struik | APM Network - Michael Court | N4, N7 | 06 July | 10 July | 4 | 0 | Not started
N10 | 0 Network | Test & document | Network As-Built document | Twiki - Shaun Struik | APM Network - Michael Court | N9 | 08 July | 15 July | 7 | 0 | Not started
N11 | 0 Network | Test & document | Patternise reusable Azure hub-spoke build template | Twiki - Michael Webster | Twiki - Shaun Struik | N10 | 13 July | 17 July | 4 | 0 | Not started
N12 ▲ | 0 Network | Test & document | MILESTONE: Network ready + patternised | Twiki - Michael Webster | APM - Murray Thomas | N9, N11 | 17 July | 17 July |  |  | Not started
1 Job Seeker
J1 ▲ | 1 Job Seeker | AVD & identity | Golden image captured (WDAC-hardened, Win11 Ent single-session) + Nerdio host pool defined — session-host deploy pending network | Twiki - Shaun Struik | Nerdio | N7 | 29 June | 10 July | 11 | 60 | In progress
J22 ▲ | 1 Job Seeker | AVD & identity | Code-signing certificate issued (D-14) + added as WDAC allowed signer (D-7) — master gate for device-side pipeline + Nerdio signing | APM Cyber - Ugbaad Adani | Twiki - Shaun Struik | — | 29 June | 08 July | 5 | 0 | Blocked
J2 | 1 Job Seeker | AVD & identity | Credential pipeline: Key Vault + Credential Proxy (EasyAuth+PRT) + rotation runbook + Hybrid Worker — blocked pending cert (J22) + network design | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N7 | 29 June | 17 July | 18 | 0 | Blocked
J3 | 1 Job Seeker | AVD & identity | Conditional Access set built — report-only until cyber re-approves (consolidate duplicate set + fix "Badge" Teams-block) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | J2 | 13 July | 17 July | 4 | 70 | In progress
J4 | 1 Job Seeker | AVD & identity | Shell Launcher + Windows App + Autopilot self-deploying profile | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J1 | 08 July | 15 July | 7 | 80 | In progress
J5 | 1 Job Seeker | AVD & identity | Lock-screen credential PR (render + LSA write) — blocked: needs cert (J22) for full-language under WDAC | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J2 | 17 July | 20 July | 3 | 0 | Blocked
J6 | 1 Job Seeker | Device test | Validate host deploy + pipeline in FVE (test env) — Nerdio CSE blocked by WDAC + missing Storage egress | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J3, J4 | 17 July | 17 July |  | 40 | In progress
J7 ▲ | 1 Job Seeker | Device test | Test device on prod network — blocked pending finalised + approved network design | Twiki - Shaun Struik | APM Network - Michael Court | N5, J6 | 20 July | 24 July | 4 | 0 | Blocked
J8 ▲ | 1 Job Seeker | Device test | MILESTONE: Test device validated on both networks | Twiki - Shaun Struik | APM - Murray Thomas | J7 | 24 July | 24 July |  |  | Not started
J9 | 1 Job Seeker | CompNow build | Finalise CompNow build instructions (wipe/prep/Autopilot/label/ship) | Twiki - Shaun Struik | CompNow | J7 | 24 July | 29 July | 5 | 0 | Not started
J10 | 1 Job Seeker | CompNow build | CompNow tests build process | CompNow | Twiki - Shaun Struik | J9 | 29 July | 31 July | 2 | 0 | Not started
J11 ▲ | 1 Job Seeker | CompNow build | Two team members test order-to-delivery end to end | Twiki - Shaun + Dave | CompNow | J10 | 31 July | 04 Aug | 4 | 0 | Not started
J12 ▲ | 1 Job Seeker | CompNow build | MILESTONE: Build process proven end to end | Twiki - Dave Badger | APM - Murray Thomas | J11 | 04 Aug | 04 Aug |  |  | Not started
J13 | 1 Job Seeker | Rollout | Pilot 5-10 devices across 2-3 sites | Twiki - Shaun + Dave | APM ES - Ben Riches | J12 | 04 Aug | 11 Aug | 7 | 0 | Not started
J14 | 1 Job Seeker | Rollout | Site network cutover JS to APM-KIOSK (rolling, per site) | APM Network - Michael Court | Twiki - Dave Badger | J8 | 11 Aug | 11 Sept | 31 | 0 | Not started
J15 | 1 Job Seeker | Rollout | Onsite device test | Twiki - Dave Badger | APM ES - Ben Riches | J13 | 11 Aug | 14 Aug | 3 | 0 | Not started
J16 | 1 Job Seeker | Rollout | National rollout (~540 devices, rolling) | Twiki - Dave Badger | CompNow | J15 | 17 Aug | 11 Sept | 25 | 0 | Not started
J17 | 1 Job Seeker | Rollout | MILESTONE: Job Seeker national rollout complete | Twiki - Dave Badger | APM ES - Ben Riches | J16 | 11 Sept | 11 Sept |  |  | Not started
2 Standard User
S1 | 2 Standard User | Document & design | Document current Intune laptop SOE + Autopilot (14 policies) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | — | 06 July | 17 July | 11 | 0 | Not started
S2 | 2 Standard User | Document & design | Close DR-010 printing + DR-011 mapped drive decisions | APM Digital Ops - Michael Barker | Twiki - Shaun Struik | — | 13 July | 24 July | 11 | 0 | Not started
S3 | 2 Standard User | Document & design | Finalise DDD V1.0 + CAB | Twiki - Shaun Struik | APM - Samit Chandra | S1, S2 | 27 July | 31 July | 4 | 0 | Not started
S4 | 2 Standard User | Document & design | MILESTONE: Standard User DDD approved | APM - Samit Chandra | APM - Murray Thomas | S3 | 31 July | 31 July |  |  | Not started
S5 | 2 Standard User | Build | Entra groups (corp/BYOD/hosts) + CA (block unmanaged, allow Windows App, context groups) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N11, S4 | 03 Aug | 12 Aug | 9 | 0 | Not started
S6 | 2 Standard User | Build | Azure Files Premium FSLogix + Entra Kerberos | Twiki - Shaun Struik | Twiki - Michael Webster | N11 | 03 Aug | 12 Aug | 9 | 0 | Not started
S7 | 2 Standard User | Build | Compute Gallery + golden image (multi-session, M365, Teams optimised) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S6 | 12 Aug | 21 Aug | 9 | 0 | Not started
S8 | 2 Standard User | Build | Nerdio pooled host pool + corp/BYOD app groups + autoscale | Twiki - Shaun Struik | Nerdio | S7 | 21 Aug | 26 Aug | 5 | 0 | Not started
S9 | 2 Standard User | Build | Scope 14 Intune policies + AVD profiles to session hosts | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S7 | 21 Aug | 26 Aug | 5 | 0 | Not started
S10 | 2 Standard User | Pilot & rollout | Pilot 25-50 users (mixed personas) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S8, S9 | 26 Aug | 04 Sept | 9 | 0 | Not started
S11 | 2 Standard User | Pilot & rollout | Validate CA from corporate + personal device | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | S5, S10 | 26 Aug | 29 Aug | 3 | 0 | Not started
S12 | 2 Standard User | Pilot & rollout | Production rollout (entitle staff, comms, Windows App self-serve) | APM EUC - Nick Dorbie | APM - Kath Nash | S10 | 07 Sept | 25 Sept | 18 | 0 | Not started
S13 | 2 Standard User | Pilot & rollout | MILESTONE: Standard User AVD GA | APM EUC - Nick Dorbie | APM - Murray Thomas | S12 | 25 Sept | 25 Sept |  |  | Not started
3 ES
E1 | 3 ES | Design adaptation | Adapt JS image: midnight daily reset (vs 10-min inactivity) | Twiki - Shaun Struik | APM ES - Ben Riches | J8 | 27 July | 31 July | 4 | 0 | Not started
E2 ▲ | 3 ES | Design adaptation | Redesign take-home: any Wi-Fi, off-site filtering (Zscaler client on device), revised CA | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | E1 | 03 Aug | 14 Aug | 11 | 0 | Not started
E3 | 3 ES | Design adaptation | ES DDD + CAB | Twiki - Shaun Struik | APM - Samit Chandra | E2 | 17 Aug | 21 Aug | 4 | 0 | Not started
E4 | 3 ES | Design adaptation | MILESTONE: ES DDD approved | APM - Samit Chandra | APM - Murray Thomas | E3 | 21 Aug | 21 Aug |  |  | Not started
E5 | 3 ES | Build & test | Build ES image/profiles (midnight reset, incl. Eskilled folder) | Twiki - Shaun Struik | APM ES - Claire McArdle | E4 | 24 Aug | 02 Sept | 9 | 0 | Not started
E6 ▲ | 3 ES | Build & test | Test off-site scenarios (home Wi-Fi, reset, filtering) | Twiki - Shaun + Dave | APM ES - Ben Riches | E5 | 02 Sept | 07 Sept | 5 | 0 | Not started
E7 | 3 ES | Rollout | Pilot + rollout (take-home devices) | Twiki - Dave Badger | APM ES - Ben Riches | E6 | 08 Sept | 18 Sept | 10 | 0 | Not started
E8 | 3 ES | Rollout | MILESTONE: ES live | Twiki - Dave Badger | APM - Murray Thomas | E7 | 18 Sept | 18 Sept |  |  | Not started
4 Privileged
P1 ▲ | 4 Privileged | Design | Privileged design: PAW-style hardened image (no mail/Teams/browse), two tiers Priv(zz)/High-Priv(xy) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N11 | 10 Aug | 21 Aug | 11 | 0 | Not started
P2 | 4 Privileged | Design | Production access model: PIM per tier, just-in-time elevation, approval + audit | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P1 | 17 Aug | 26 Aug | 9 | 0 | Not started
P3 | 4 Privileged | Design | Privileged Access DDD + CAB | Twiki - Shaun Struik | APM - Samit Chandra | P2 | 24 Aug | 28 Aug | 4 | 0 | Not started
P4 | 4 Privileged | Design | MILESTONE: Privileged DDD approved | APM - Samit Chandra | APM Cyber - Ugbaad Adani | P3 | 28 Aug | 28 Aug |  |  | Not started
P5 ▲ | 4 Privileged | YubiKey | Test YubiKey 5C NFC FIPS (phishing-resistant MFA for zz/xy) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P1 | 17 Aug | 26 Aug | 9 | 0 | Not started
P6 ▲ | 4 Privileged | YubiKey | MILESTONE: YubiKey 5C NFC FIPS validated | APM Cyber - Ugbaad Adani | Twiki - Shaun Struik | P5 | 26 Aug | 26 Aug |  |  | Not started
P7 ▲ | 4 Privileged | Build | Build hardened Privileged image + secure pool | Twiki - Shaun Struik | Twiki - Michael Webster | P4 | 31 Aug | 09 Sept | 9 | 0 | Not started
P8 ▲ | 4 Privileged | Build | CA + PIM for Priv(zz) & High-Priv(xy) production scopes; YubiKey-only sign-in | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P6, P7 | 09 Sept | 16 Sept | 7 | 0 | Not started
P9 | 4 Privileged | Pilot & cutover | Pilot privileged users (both tiers) + validate prod access via YubiKey | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P8 | 16 Sept | 23 Sept | 7 | 0 | Not started
P10 ▲ | 4 Privileged | Pilot & cutover | MILESTONE: Privileged Access live (zz + xy) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P9 | 23 Sept | 23 Sept |  |  | Not started
5 Developer
D1 | 5 Developer | Design | Finalise Dev DDD: permissive dev image, limited blocks, no production-access path | Twiki - Shaun Struik | APM - Samit Chandra | N11 | 24 Aug | 02 Sept | 9 | 0 | Not started
D2 | 5 Developer | Design | Design Dev network from JS pattern + adjust (deny-by-default egress, Zscaler at endpoint) | Twiki - Shaun Struik | APM Network - Michael Court | N11 | 31 Aug | 04 Sept | 4 | 0 | Not started
D3 | 5 Developer | Build | AVD landing zone (Bicep) + FSLogix Premium ZRS + Sentinel + Entra groups | Twiki - Shaun Struik | Twiki - Michael Webster | D1, D2 | 07 Sept | 14 Sept | 7 | 0 | Not started
D4 | 5 Developer | Build | AIB image pipeline (Git template, signing, SBOM) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | D3 | 09 Sept | 16 Sept | 7 | 0 | Not started
D5 | 5 Developer | Build | Primary pooled host pool + scaling plan (nested virtualisation) | Twiki - Shaun Struik | Nerdio | D4 | 14 Sept | 18 Sept | 5 | 0 | Not started
D6 | 5 Developer | Build | Dev tooling layers (VS, Podman/containers, WSL2) with limited blocks | Twiki - Shaun Struik | APM EUC - Nick Dorbie | D5 | 16 Sept | 23 Sept | 7 | 0 | Not started
D7 | 5 Developer | Pilot & GA | Pilot ring (PDE owner + cohort) + smoke test + CA enforced | Twiki - Shaun Struik | APM - PDE owner (TBC) | D5 | 21 Sept | 25 Sept | 4 | 0 | Not started
D8 | 5 Developer | Pilot & GA | Team-by-team migration from legacy PDE | Twiki - Shaun Struik | APM EUC - Nick Dorbie | D7 | 25 Sept | 02 Oct | 7 | 0 | Not started
D9 | 5 Developer | Pilot & GA | Capability phases 2-3 (winget/ACR; Copilot/MCP/local LLM) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | D8 | 28 Sept | 09 Oct | 11 | 0 | Not started
D10 | 5 Developer | Pilot & GA | Retire legacy PDE after 1 month stable | Twiki - Shaun Struik | APM Digital Ops - Michael Barker | D8 | 09 Oct | 16 Oct | 7 | 0 | Not started
D11 ▲ | 5 Developer | Pilot & GA | MILESTONE: Developer SOE GA (past 30 Sep on current resourcing) | Twiki - Shaun Struik | APM - Murray Thomas | D8, D9 | 09 Oct | 09 Oct |  |  | Not started
6 Logistics
L1 | 6 Logistics | Job Seeker | Retrieve old JS devices onsite + place new (rolling) | Twiki - Dave Badger | APM ES - Ben Riches | J12 | 11 Aug | 11 Sept | 31 | 0 | Not started
L2 | 6 Logistics | All | Asset register updates (ongoing) | Twiki - Dave Badger | APM EUC - Nick Dorbie | — | 04 Aug | 30 Sept | 57 | 0 | Not started
L3 | 6 Logistics | Standard User | Retrieve standard-user laptops as AVD replaces | Twiki - Dave Badger | APM EUC - Nick Dorbie | S13 | 07 Sept | 30 Sept | 23 | 0 | Not started
L4 | 6 Logistics | Privileged | Retrieve/contract high-priv laptops to users on own Macs (via Privileged image) | Twiki - Dave Badger | APM - Murray Thomas | P10 | 23 Sept | 30 Sept | 7 | 0 | Not started
7 KB & Enablement
K1 | 7 KB & Enablement | Network | KB: APM-KIOSK build/cutover + Azure hub-spoke pattern | Twiki - Shaun (build) | Kath Nash -> Michael Court | N10 | 13 July | 20 July | 7 | 0 | Not started
K2 | 7 KB & Enablement | Job Seeker | KB: CompNow wipe/prep/ship process | Twiki - Shaun (build) | Kath Nash -> CompNow | J9 | 24 July | 29 July | 5 | 0 | Not started
K3 | 7 KB & Enablement | Job Seeker | KB: JS ops (password rotation, lock screen, site cutover, device replace) | Twiki - Shaun (build) | Kath Nash -> Nick Dorbie / Rohit Singh | J5 | 27 July | 10 Aug | 14 | 0 | Not started
K4 | 7 KB & Enablement | Standard User | KB: image/patch, FSLogix lifecycle, CA BYOD, Windows App onboarding | Twiki - Shaun (build) | Kath Nash -> Nick Dorbie | S8 | 26 Aug | 07 Sept | 12 | 0 | Not started
K5 | 7 KB & Enablement | ES | KB: ES midnight reset, off-site connectivity, Eskilled access | Twiki - Shaun (build) | Kath Nash -> Ben Riches / Rohit Singh | E5 | 24 Aug | 02 Sept | 9 | 0 | Not started
K6 | 7 KB & Enablement | Privileged | KB: Privileged access request, PIM per tier (zz/xy), YubiKey enrolment | Twiki - Shaun (build) | Kath Nash -> Ugbaad Adani / Rohit Singh | P7 | 09 Sept | 18 Sept | 9 | 0 | Not started
K7 | 7 KB & Enablement | Developer | KB: Dev image pipeline/rollback, self-service tooling, MCP request, FSLogix recovery | Twiki - Shaun (build) | Kath Nash -> PDE owner / Rohit Singh | D6 | 23 Sept | 02 Oct | 9 | 0 | Not started
K8 | 7 KB & Enablement | Service Desk | KB: Tier-1 Service Desk triage runbooks (all use cases) | Twiki - Shaun (build) | Kath Nash -> Rohit Singh | K3 | 14 Sept | 30 Sept | 16 | 0 | Not started

## Gantt Chart
Gantt Chart — week commencing (Mon). Bars by workstream · ◆ milestone
ID | Task | Owner | 22 June | 29 June | 06 July | 13 July | 20 July | 27 July | 03 Aug | 10 Aug | 17 Aug | 24 Aug | 31 Aug | 07 Sept | 14 Sept | 21 Sept | 28 Sept | 05 Oct | 12 Oct | 19 Oct
0 Network
N1 ▲ | Repurpose JS VLAN to APM-KIOSK (VLAN 73), hidden SSID + PSK via Intune | APM Network - Michael Court
N2 ▲ | Meraki per-site /26 template, 20Mbps, remove CAPTCHA | APM Network - Michael Court
N3 ▲ | Palo Alto east-west firewall rules (kiosk to AVD, deny-all) | APM Network - Michael Court
N4 ▲ | Zscaler IPSEC tunnel (Stratus) cutover from ZCC | APM Network - Michael Court
N5 ▲ | MILESTONE: Network build target | APM Network - Michael Court | ◆
N6 ▲ | Hub VNet - DNS Private Resolver, NAT GW, shared services | Twiki - Michael Webster
N7 ▲ | AVD spoke VNet, NSGs, private endpoints (KV/Files/Func) | Twiki - Shaun Struik
N8 | DNS Private Resolver zones + FQDN allowlist validation | Twiki - Shaun Struik
N9 ▲ | Test network end-to-end (AVD FQDNs, Key Vault, Zscaler path) | Twiki - Shaun Struik
N10 | Network As-Built document | Twiki - Shaun Struik
N11 | Patternise reusable Azure hub-spoke build template | Twiki - Michael Webster
N12 ▲ | MILESTONE: Network ready + patternised | Twiki - Michael Webster |  |  |  | ◆
1 Job Seeker
J1 ▲ | Golden image captured (WDAC-hardened, Win11 Ent single-session) + Nerdio host pool defined — session-host deploy pending network | Twiki - Shaun Struik
J22 ▲ | Code-signing certificate issued (D-14) + added as WDAC allowed signer (D-7) — master gate for device-side pipeline + Nerdio signing | APM Cyber - Ugbaad Adani
J2 | Credential pipeline: Key Vault + Credential Proxy (EasyAuth+PRT) + rotation runbook + Hybrid Worker — blocked pending cert (J22) + network design | Twiki - Shaun Struik
J3 | Conditional Access set built — report-only until cyber re-approves (consolidate duplicate set + fix "Badge" Teams-block) | Twiki - Shaun Struik
J4 | Shell Launcher + Windows App + Autopilot self-deploying profile | Twiki - Shaun Struik
J5 | Lock-screen credential PR (render + LSA write) — blocked: needs cert (J22) for full-language under WDAC | Twiki - Shaun Struik
J6 | Validate host deploy + pipeline in FVE (test env) — Nerdio CSE blocked by WDAC + missing Storage egress | Twiki - Shaun Struik
J7 ▲ | Test device on prod network — blocked pending finalised + approved network design | Twiki - Shaun Struik
J8 ▲ | MILESTONE: Test device validated on both networks | Twiki - Shaun Struik |  |  |  |  | ◆
J9 | Finalise CompNow build instructions (wipe/prep/Autopilot/label/ship) | Twiki - Shaun Struik
J10 | CompNow tests build process | CompNow
J11 ▲ | Two team members test order-to-delivery end to end | Twiki - Shaun + Dave
J12 ▲ | MILESTONE: Build process proven end to end | Twiki - Dave Badger | [6 empty] | ◆
J13 | Pilot 5-10 devices across 2-3 sites | Twiki - Shaun + Dave
J14 | Site network cutover JS to APM-KIOSK (rolling, per site) | APM Network - Michael Court
J15 | Onsite device test | Twiki - Dave Badger
J16 | National rollout (~540 devices, rolling) | Twiki - Dave Badger
J17 | MILESTONE: Job Seeker national rollout complete | Twiki - Dave Badger | [11 empty] | ◆
2 Standard User
S1 | Document current Intune laptop SOE + Autopilot (14 policies) | Twiki - Shaun Struik
S2 | Close DR-010 printing + DR-011 mapped drive decisions | APM Digital Ops - Michael Barker
S3 | Finalise DDD V1.0 + CAB | Twiki - Shaun Struik
S4 | MILESTONE: Standard User DDD approved | APM - Samit Chandra | [5 empty] | ◆
S5 | Entra groups (corp/BYOD/hosts) + CA (block unmanaged, allow Windows App, context groups) | Twiki - Shaun Struik
S6 | Azure Files Premium FSLogix + Entra Kerberos | Twiki - Shaun Struik
S7 | Compute Gallery + golden image (multi-session, M365, Teams optimised) | Twiki - Shaun Struik
S8 | Nerdio pooled host pool + corp/BYOD app groups + autoscale | Twiki - Shaun Struik
S9 | Scope 14 Intune policies + AVD profiles to session hosts | Twiki - Shaun Struik
S10 | Pilot 25-50 users (mixed personas) | Twiki - Shaun Struik
S11 | Validate CA from corporate + personal device | Twiki - Shaun Struik
S12 | Production rollout (entitle staff, comms, Windows App self-serve) | APM EUC - Nick Dorbie
S13 | MILESTONE: Standard User AVD GA | APM EUC - Nick Dorbie | [13 empty] | ◆
3 ES
E1 | Adapt JS image: midnight daily reset (vs 10-min inactivity) | Twiki - Shaun Struik
E2 ▲ | Redesign take-home: any Wi-Fi, off-site filtering (Zscaler client on device), revised CA | Twiki - Shaun Struik
E3 | ES DDD + CAB | Twiki - Shaun Struik
E4 | MILESTONE: ES DDD approved | APM - Samit Chandra | [8 empty] | ◆
E5 | Build ES image/profiles (midnight reset, incl. Eskilled folder) | Twiki - Shaun Struik
E6 ▲ | Test off-site scenarios (home Wi-Fi, reset, filtering) | Twiki - Shaun + Dave
E7 | Pilot + rollout (take-home devices) | Twiki - Dave Badger
E8 | MILESTONE: ES live | Twiki - Dave Badger | [12 empty] | ◆
4 Privileged
P1 ▲ | Privileged design: PAW-style hardened image (no mail/Teams/browse), two tiers Priv(zz)/High-Priv(xy) | Twiki - Shaun Struik
P2 | Production access model: PIM per tier, just-in-time elevation, approval + audit | Twiki - Shaun Struik
P3 | Privileged Access DDD + CAB | Twiki - Shaun Struik
P4 | MILESTONE: Privileged DDD approved | APM - Samit Chandra | [9 empty] | ◆
P5 ▲ | Test YubiKey 5C NFC FIPS (phishing-resistant MFA for zz/xy) | Twiki - Shaun Struik
P6 ▲ | MILESTONE: YubiKey 5C NFC FIPS validated | APM Cyber - Ugbaad Adani | [9 empty] | ◆
P7 ▲ | Build hardened Privileged image + secure pool | Twiki - Shaun Struik
P8 ▲ | CA + PIM for Priv(zz) & High-Priv(xy) production scopes; YubiKey-only sign-in | Twiki - Shaun Struik
P9 | Pilot privileged users (both tiers) + validate prod access via YubiKey | Twiki - Shaun Struik
P10 ▲ | MILESTONE: Privileged Access live (zz + xy) | Twiki - Shaun Struik | [13 empty] | ◆
5 Developer
D1 | Finalise Dev DDD: permissive dev image, limited blocks, no production-access path | Twiki - Shaun Struik
D2 | Design Dev network from JS pattern + adjust (deny-by-default egress, Zscaler at endpoint) | Twiki - Shaun Struik
D3 | AVD landing zone (Bicep) + FSLogix Premium ZRS + Sentinel + Entra groups | Twiki - Shaun Struik
D4 | AIB image pipeline (Git template, signing, SBOM) | Twiki - Shaun Struik
D5 | Primary pooled host pool + scaling plan (nested virtualisation) | Twiki - Shaun Struik
D6 | Dev tooling layers (VS, Podman/containers, WSL2) with limited blocks | Twiki - Shaun Struik
D7 | Pilot ring (PDE owner + cohort) + smoke test + CA enforced | Twiki - Shaun Struik
D8 | Team-by-team migration from legacy PDE | Twiki - Shaun Struik
D9 | Capability phases 2-3 (winget/ACR; Copilot/MCP/local LLM) | Twiki - Shaun Struik
D10 | Retire legacy PDE after 1 month stable | Twiki - Shaun Struik
D11 ▲ | MILESTONE: Developer SOE GA (past 30 Sep on current resourcing) | Twiki - Shaun Struik | [15 empty] | ◆
6 Logistics
L1 | Retrieve old JS devices onsite + place new (rolling) | Twiki - Dave Badger
L2 | Asset register updates (ongoing) | Twiki - Dave Badger
L3 | Retrieve standard-user laptops as AVD replaces | Twiki - Dave Badger
L4 | Retrieve/contract high-priv laptops to users on own Macs (via Privileged image) | Twiki - Dave Badger
7 KB & Enablement
K1 | KB: APM-KIOSK build/cutover + Azure hub-spoke pattern | Twiki - Shaun (build)
K2 | KB: CompNow wipe/prep/ship process | Twiki - Shaun (build)
K3 | KB: JS ops (password rotation, lock screen, site cutover, device replace) | Twiki - Shaun (build)
K4 | KB: image/patch, FSLogix lifecycle, CA BYOD, Windows App onboarding | Twiki - Shaun (build)
K5 | KB: ES midnight reset, off-site connectivity, Eskilled access | Twiki - Shaun (build)
K6 | KB: Privileged access request, PIM per tier (zz/xy), YubiKey enrolment | Twiki - Shaun (build)
K7 | KB: Dev image pipeline/rollback, self-service tooling, MCP request, FSLogix recovery | Twiki - Shaun (build)
K8 | KB: Tier-1 Service Desk triage runbooks (all use cases) | Twiki - Shaun (build)

## Stakeholders & RACI
Stakeholders & RACI
Name | Org | Role | Accountable / Owns | Reports to
Murray Thomas | APM | Digital Delivery Portfolio Manager | This project - decision authority & escalation. Shaun + Dave report here. | -
Nathan Heaton | APM | Program Manager (overall) | Program-level coordination across projects | -
Samit Chandra | APM | Head of Digital Transformation & Architecture | DDD owner; architecture authority; Dev requirements sign-off | -
Jensen Spencer | APM | CTO / CISO | Executive authority — delegates delivery and sign-off to department heads | -
Michael Barker | APM | Head of Digital Operations | Operations; SSID approval; Dev support model; PDE decommission | Jensen Spencer
Michael Court | APM | IT Infrastructure Lead | Network & infrastructure build (site + Azure) | Jensen Spencer (assumed)
Ugbaad Adani | APM | Cyber Security | Cyber controls, RFFR assurance, CA/PIM, Privileged Access + YubiKey | Jensen Spencer (assumed)
Nick Dorbie | APM | End User Compute Manager | EUC build/operations, Intune | Michael Barker (assumed)
Rohit Singh | APM | IT Service Lead / Service Desk | Support, triage runbooks | Michael Barker (assumed)
Kath Nash | APM | Digital Business Partner | All instructions + comms; KB validation | Michael Barker (assumed)
Ben Riches | APM | ES Lead | Business owner: Job Seeker, ES (take-home), ES devices | -
James Muller | APM | CEO Employment Services | Executive sponsor | -
Claire McArdle | APM | ES (Eskilled) | ES Eskilled training content | -
PDE owner | APM | To be nominated | Developer platform owner (Dev service catalogue, image approval) | Michael Barker (assumed)
Michael Webster | Twiki Corp | Architecture Lead (Azure, Cloud, Security) | Solution architecture | Samit Chandra
Shaun Struik | Twiki Corp | Solution Engineer AVD | AVD build & delivery; KB authoring | Murray Thomas
David Badger | Twiki Corp | Project Manager | PM + device logistics / retrieval | Murray Thomas
CompNow | External | Device partner | Device wipe/prep/build/ship | -
Nerdio | External | AVD orchestration platform | Host pool management, autoscale, reimaging | -

## KB Register
KB Register — build by Shaun Struik → validate Kath Nash → validate process stakeholder → publish (APM KB standard)
KB ID | Workstream | Process / KB Title | Built by | Validate 1 | Validate 2 (stakeholder) | Owning team | Status
KB-N1 | 0 Network | APM-KIOSK site network build & site cutover | Shaun Struik | Kath Nash | Michael Court | Network | Not started
KB-N2 | 0 Network | Azure hub-spoke reusable build pattern | Shaun Struik | Kath Nash | Michael Webster | Cloud / Azure | Not started
KB-J1 | 1 Job Seeker | CompNow device wipe / prep / Autopilot / label / ship · drafted: CN-JSK-01, CN-JSK-02 | Shaun Struik | Kath Nash | CompNow + Nick Dorbie | EUC / Vendor | Drafted
KB-J2 | 1 Job Seeker | Kiosk password rotation runbook (Azure Automation) · drafted: KB-JSK-03, KB-JSK-04 | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Drafted
KB-J3 | 1 Job Seeker | Lock screen proactive remediation · drafted: KB-JSK-09 | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Drafted
KB-J4 | 1 Job Seeker | F3 account create / retire runbook · drafted: KB-JSK-01 | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Drafted
KB-J5 | 1 Job Seeker | Site VLAN to APM-KIOSK cutover (per site) | Shaun Struik | Kath Nash | Michael Court | Network | Not started
KB-J6 | 1 Job Seeker | Kiosk device replacement / RMA · drafted: KB-JSK-05, KB-JSK-06, KB-JSK-07, CN-JSK-03 | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Drafted
KB-J7 | 1 Job Seeker | Golden image build & patch (CLI-only, WDAC-hardened) · drafted: WP-2.10 GoldenImage CLIOnly + ExecutionSheet, golden-image-build/* | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Drafted
KB-J8 | 1 Job Seeker | Nerdio scripted-action signing under WDAC + session-host App Control allowed signer · drafted: nerdio-scripts-signing-wdac, cyber note 24 Jun | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Drafted
KB-J9 | 1 Job Seeker | Shell Launcher / Assigned Access kiosk shell + Windows App onboarding · drafted: shell-launcher/*, windows-app-kiosk/* | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Drafted
KB-S1 | 2 Standard User | Golden image build & monthly patch (Nerdio) | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-S2 | 2 Standard User | FSLogix profile lifecycle (create/snapshot/restore/deprovision) | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-S3 | 2 Standard User | CA BYOD vs corporate troubleshooting | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Not started
KB-S4 | 2 Standard User | Windows App onboarding (corporate + BYOD) | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started
KB-S5 | 2 Standard User | Host pool scaling / capacity management | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-E1 | 3 ES | ES midnight reset operation | Shaun Struik | Kath Nash | Ben Riches | ES | Not started
KB-E2 | 3 ES | ES off-site connectivity (any Wi-Fi) + filtering | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started
KB-E3 | 3 ES | Eskilled access (ES) | Shaun Struik | Kath Nash | Claire McArdle | ES | Not started
KB-P1 | 4 Privileged | Privileged Access request & approval (Priv zz / High-Priv xy) | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P2 | 4 Privileged | PIM elevation per tier (production access) | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P3 | 4 Privileged | YubiKey 5C NFC FIPS enrolment | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P4 | 4 Privileged | Privileged image build & hardening | Shaun Struik | Kath Nash | Michael Webster | Cloud / Cyber | Not started
KB-D1 | 5 Developer | AIB image pipeline + rollback | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D2 | 5 Developer | Dev self-service tooling (winget / Company Portal) | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D3 | 5 Developer | MCP server request / allowlist | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D4 | 5 Developer | OIDC deployment pipeline request | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D5 | 5 Developer | FSLogix profile recovery (Dev) | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-SD1 | 7 KB & Enablement | Tier-1 Service Desk triage runbooks (all use cases) · drafted: KB-JSK-02, KB-JSK-10 | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Drafted

## Assumptions & Risks
Assumptions, Risks & Open Decisions
# | Risk / Assumption / Open decision | Impact | Likelihood | Owner | Mitigation / Recommendation
1 | APM is running several tier-one projects in parallel. The AVD program's schedule depends on APM departments (Network, Cyber, EUC) and decision-makers completing their inputs on time. Contention for APM resources and approvals — not delivery capacity — is the primary risk to the 30 Sep dates. | High | High | Murray Thomas / Twiki | Lock an APM owner and a due date for every dependency (network build, DR-010/011 decisions, pen-test window, PDE owner). Weekly dependency review with the Portfolio Manager; escalate any APM-side slippage immediately.
2 | Network (site + Azure) is on the critical path from day one and is delivered by APM Network / Infrastructure. Any APM-side network slippage directly delays Job Seeker testing and the national rollout. | High | Med | Michael Court / Michael Webster | Confirm APM Network resourcing now and hold a daily stand-up until the network is proven. Twiki supports the Azure foundation.
3 | Privileged Access is a net-new design (PAW-style, two tiers zz/xy, YubiKey) added mid-window. It carries the production-access blast-radius risk. | High | Med | Shaun Struik / Ugbaad Adani (Cyber) | Design once, gate hard on YubiKey. The Cyber lead (Ugbaad Adani) signs off the privileged model. Do not cut over high-priv until P6 (YubiKey validated) and P8 (CA/PIM) pass.
4 | YubiKey 5C NFC FIPS now gates Privileged production access for zz/xy. If it fails, no phishing-resistant path to production from Macs. | High | Med | Shaun / Ugbaad Adani | Run the YubiKey test early (week of 17 Aug). Fallback to a dedicated hardened Cloud PC for the highest tier if FIPS keys do not validate.
5 | ES take-home (was CTA) breaks the site-VLAN / PSK / site-Zscaler controls Job Seeker relies on. It is a security redesign, now 3rd in order. | High | High | Shaun / Ugbaad Adani | Treat ES as its own design (Zscaler client on device, revised CA, any Wi-Fi, midnight reset). Confirm Eskilled access path with Claire McArdle.
6 | Developer is a separate permissive image (limited blocks, no production path). Production access lives only in the Privileged image. | Med | Low | Shaun / Samit Chandra | Keep the boundary clean: no production scopes on the Dev pool. Samit Chandra signs off Dev requirements.
7 | Standard User printing (DR-010) and mapped drive (DR-011) still pending. Both gate the SU build. | Med | High | Michael Barker / Nick Dorbie | Force decisions by 24 Jul. Universal Print is the likely path. Confirm mapped-drive backend (SharePoint / Azure Files / on-prem).
8 | RESOLVED — Job Seeker device count confirmed at 540 (early drafts showed 517 vs 540). | Low | Low | Dave Badger / Nick Dorbie | Done — 540 is the confirmed count, applied everywhere (licensing + site allocation).
9 | Nerdio assumed already deployed and operational. Standard User, ES and Developer all reuse it. | High | Low | Shaun / Michael Webster | Confirm Nerdio is live in the tenant. If not, add a deployment task that gates the Job Seeker AVD build.
10 | Developer PDE owner not yet named. Gates Dev pilot, image approval and the Dev service catalogue. | Med | Med | Murray Thomas / Michael Barker | Nominate the APM PDE owner now so Dev pilot and KB validation have an APM stakeholder.
11 | Contract ends 30 Sep with little buffer. The exposure is APM-side dependencies (network completion, security sign-off / pen-test scheduling, approvals) landing late — not delivery throughput. | High | High | Murray Thomas | Confirm APM dependency dates now and agree what 'done by 30 Sep' means per use case (live, piloted, designed). Protect Privileged from descoping.
12 | JOB SEEKER — Code-signing certificate (D-14) is the master gate. One fleet-trusted cert, added as a WDAC allowed signer (D-7), unblocks the entire device-side credential pipeline (token fetch, lock-screen render, LSA write) and Nerdio session-host script signing. Until it is issued, the credential pipeline cannot complete. | High | High | APM Cyber - Ugbaad Adani | Issue the cert and add it as an allowed signer via a signed supplemental policy (signer rule, not hash/path). One cert closes the kiosk device-side scripts and the Nerdio session-host scripts together.
13 | JOB SEEKER — Credential Proxy public ingress (D-3) is the single biggest unverified link. With no site→Azure private path today, remote kiosks can only reach the Function App via a hardened public ingress. | High | Med | APM Cyber - Ugbaad Adani / Twiki - Shaun Struik | Confirm a hardened EasyAuth-protected public ingress (Entra-validated, returns only the calling device's secret). Migrate the pilot's per-device function-key build to EasyAuth+PRT (C-6).
14 | JOB SEEKER — Network design must be finalised + approved by APM before any networking or credential-pipeline deploys; the temporary public-endpoint workaround was rejected. The live build runs in the FVE (test), not prod. | High | Med | APM Network - Vijay Natakar / APM Cyber | Lock an APM owner and date for the finalised network design. Add NSG Storage/MCR egress (D-5) so the Nerdio CSE host deploy stops failing (HTTP 403 / Device Guard 4551).