## Program Plan
APM Digital Workplace - AVD Program Plan & Gantt
Delivery: Twiki Corp ¦ Order: Job Seeker, Standard User, ES, Privileged, Developer ¦ Window: 23 Jun - 30 Sep 2026 (contract end) ¦ Network target: 26 Jun ¦ Edit Start/End/% and bars, dep checks and chart update live
ES = Employment Services take-home device (was CTA). Privileged = production access at two tiers: Priv (zz) and High-Priv (xy), YubiKey-gated. Bars by workstream ¦ green = % done ¦ gold = milestone ¦ red = critical ¦ grey = today ¦ Dep check = Overlap where a task starts before a predecessor finishes | [15 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
ID | Workstream | Phase | Task | Owner (Accountable) | Support (Responsible) | Depends | Start | End | Days | % | Status | Latest pred finish | Dep check | Type | Crit | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12
N1 | 0 Network | Site network | Repurpose JS VLAN to APM-KIOSK (VLAN 73), hidden SSID + PSK via Intune | APM Network - Michael Court | Twiki - Shaun Struik | - | 2026-06-23 | 2026-06-26 | 4 | 0% | In progress |  | - | Task | Y | [17 empty] | 2026-06-23 | 3
N2 | 0 Network | Site network | Meraki per-site /26 template, 20Mbps, remove CAPTCHA | APM Network - Michael Court | Twiki - Michael Webster | - | 2026-06-23 | 2026-06-26 | 4 | 0% | In progress |  | - | Task | Y | [17 empty] | 2026-06-23 | 3
N3 | 0 Network | Site network | Palo Alto east-west firewall rules (kiosk to AVD, deny-all) | APM Network - Michael Court | APM Cyber - Ugbaad Adani | N1 | 2026-06-24 | 2026-07-01 | 6 | 0% | Not started | 2026-06-26 | Overlap | Task | Y | [17 empty] | 2026-06-24 | 7
N4 | 0 Network | Site network | Zscaler IPSEC tunnel (Stratus) cutover from ZCC | APM Network - Michael Court | APM Cyber - Ugbaad Adani | N3 | 2026-06-25 | 2026-07-03 | 7 | 0% | Not started | 2026-07-01 | Overlap | Task | Y | [17 empty] | 2026-06-25 | 8
N5 | 0 Network | Site network | MILESTONE: Network build target | APM Network - Michael Court | Twiki - Shaun Struik | N1,N2 | 2026-06-26 | 2026-06-26 |  | 0% | Not started | 2026-06-26 | OK | Milestone | Y | [17 empty] | 2026-06-26 | 1
N6 | 0 Network | Azure foundation | Hub VNet - DNS Private Resolver, NAT GW, shared services | Twiki - Michael Webster | Twiki - Shaun Struik | - | 2026-06-23 | 2026-07-03 | 9 | 0% | In progress |  | - | Task | Y | [17 empty] | 2026-06-23 | 10
N7 | 0 Network | Azure foundation | AVD spoke VNet, NSGs, private endpoints (KV/Files/Func) | Twiki - Shaun Struik | Twiki - Michael Webster | N6 | 2026-06-29 | 2026-07-08 | 8 | 0% | Not started | 2026-07-03 | Overlap | Task | Y | [17 empty] | 2026-06-29 | 9
N8 | 0 Network | Azure foundation | DNS Private Resolver zones + FQDN allowlist validation | Twiki - Shaun Struik | APM Network - Michael Court | N7 | 2026-07-06 | 2026-07-10 | 5 | 0% | Not started | 2026-07-08 | Overlap | Task | [18 empty] | 2026-07-06 | 4
N9 | 0 Network | Test & document | Test network end-to-end (AVD FQDNs, Key Vault, Zscaler path) | Twiki - Shaun Struik | APM Network - Michael Court | N4,N7 | 2026-07-06 | 2026-07-10 | 5 | 0% | Not started | 2026-07-08 | Overlap | Task | Y | [17 empty] | 2026-07-06 | 4
N10 | 0 Network | Test & document | Network As-Built document | Twiki - Shaun Struik | APM Network - Michael Court | N9 | 2026-07-08 | 2026-07-15 | 6 | 0% | Not started | 2026-07-10 | Overlap | Task | [18 empty] | 2026-07-08 | 7
N11 | 0 Network | Test & document | Patternise reusable Azure hub-spoke build template | Twiki - Michael Webster | Twiki - Shaun Struik | N10 | 2026-07-13 | 2026-07-17 | 5 | 0% | Not started | 2026-07-15 | Overlap | Task | [18 empty] | 2026-07-13 | 4
N12 | 0 Network | Test & document | MILESTONE: Network ready + patternised | Twiki - Michael Webster | APM - Murray Thomas | N9,N11 | 2026-07-17 | 2026-07-17 |  | 0% | Not started | 2026-07-17 | OK | Milestone | Y | [17 empty] | 2026-07-17 | 1
J1 | 1 Job Seeker | AVD & identity | Nerdio host pool HP-APM-Kiosk + golden image (Win11 IoT/Ent) | Twiki - Shaun Struik | Nerdio | N7 | 2026-06-29 | 2026-07-10 | 10 | 0% | Not started | 2026-07-08 | Overlap | Task | Y | [17 empty] | 2026-06-29 | 11
J2 | 1 Job Seeker | AVD & identity | Entra groups + F3 account runbook + Key Vault + Credential Proxy + Hybrid Worker | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N7 | 2026-06-29 | 2026-07-17 | 15 | 0% | Not started | 2026-07-08 | Overlap | Task | [18 empty] | 2026-06-29 | 18
J3 | 1 Job Seeker | AVD & identity | Conditional Access (device-bound, web-only, block non-Win/web client) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | J2 | 2026-07-13 | 2026-07-17 | 5 | 0% | Not started | 2026-07-17 | Overlap | Task | [18 empty] | 2026-07-13 | 4
J4 | 1 Job Seeker | AVD & identity | Shell Launcher + Windows App + Autopilot self-deploying profile | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J1 | 2026-07-08 | 2026-07-15 | 6 | 0% | Not started | 2026-07-10 | Overlap | Task | [18 empty] | 2026-07-08 | 7
J5 | 1 Job Seeker | AVD & identity | Lock screen proactive remediation (password + wallpaper) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J2 | 2026-07-17 | 2026-07-20 | 2 | 0% | Not started | 2026-07-17 | OK | Task | [18 empty] | 2026-07-17 | 3
J6 | 1 Job Seeker | Device test | Test device on test network | Twiki - Shaun Struik | APM EUC - Nick Dorbie | J3,J4 | 2026-07-17 | 2026-07-17 | 1 | 0% | Not started | 2026-07-17 | OK | Task | [18 empty] | 2026-07-17 | 1
J7 | 1 Job Seeker | Device test | Test device on test + production network | Twiki - Shaun Struik | APM Network - Michael Court | N5,J6 | 2026-07-20 | 2026-07-24 | 5 | 0% | Not started | 2026-07-17 | OK | Task | Y | [17 empty] | 2026-07-20 | 4
J8 | 1 Job Seeker | Device test | MILESTONE: Test device validated on both networks | Twiki - Shaun Struik | APM - Murray Thomas | J7 | 2026-07-24 | 2026-07-24 |  | 0% | Not started | 2026-07-24 | OK | Milestone | Y | [17 empty] | 2026-07-24 | 1
J9 | 1 Job Seeker | CompNow build | Finalise CompNow build instructions (wipe/prep/Autopilot/label/ship) | Twiki - Shaun Struik | CompNow | J7 | 2026-07-24 | 2026-07-29 | 4 | 0% | Not started | 2026-07-24 | OK | Task | [18 empty] | 2026-07-24 | 5
J10 | 1 Job Seeker | CompNow build | CompNow tests build process | CompNow | Twiki - Shaun Struik | J9 | 2026-07-29 | 2026-07-31 | 3 | 0% | Not started | 2026-07-29 | OK | Task | [18 empty] | 2026-07-29 | 2
J11 | 1 Job Seeker | CompNow build | Two team members test order-to-delivery end to end | Twiki - Shaun + Dave | CompNow | J10 | 2026-07-31 | 2026-08-04 | 3 | 0% | Not started | 2026-07-31 | OK | Task | Y | [17 empty] | 2026-07-31 | 4
J12 | 1 Job Seeker | CompNow build | MILESTONE: Build process proven end to end | Twiki - Dave Badger | APM - Murray Thomas | J11 | 2026-08-04 | 2026-08-04 |  | 0% | Not started | 2026-08-04 | OK | Milestone | Y | [17 empty] | 2026-08-04 | 1
J13 | 1 Job Seeker | Rollout | Pilot 5-10 devices across 2-3 sites | Twiki - Shaun + Dave | APM ES - Ben Riches | J12 | 2026-08-04 | 2026-08-11 | 6 | 0% | Not started | 2026-08-04 | OK | Task | [18 empty] | 2026-08-04 | 7
J14 | 1 Job Seeker | Rollout | Site network cutover JS to APM-KIOSK (rolling, per site) | APM Network - Michael Court | Twiki - Dave Badger | J8 | 2026-08-11 | 2026-09-11 | 24 | 0% | Not started | 2026-07-24 | OK | Task | [18 empty] | 2026-08-11 | 31
J15 | 1 Job Seeker | Rollout | Onsite device test | Twiki - Dave Badger | APM ES - Ben Riches | J13 | 2026-08-11 | 2026-08-14 | 4 | 0% | Not started | 2026-08-11 | OK | Task | [18 empty] | 2026-08-11 | 3
J16 | 1 Job Seeker | Rollout | National rollout (~517 devices, rolling) | Twiki - Dave Badger | CompNow | J15 | 2026-08-17 | 2026-09-11 | 20 | 0% | Not started | 2026-08-14 | OK | Task | [18 empty] | 2026-08-17 | 25
J17 | 1 Job Seeker | Rollout | MILESTONE: Job Seeker national rollout complete | Twiki - Dave Badger | APM ES - Ben Riches | J16 | 2026-09-11 | 2026-09-11 |  | 0% | Not started | 2026-09-11 | OK | Milestone | [18 empty] | 2026-09-11 | 1
S1 | 2 Standard User | Document & design | Document current Intune laptop SOE + Autopilot (14 policies) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | - | 2026-07-06 | 2026-07-17 | 10 | 0% | Not started |  | - | Task | [18 empty] | 2026-07-06 | 11
S2 | 2 Standard User | Document & design | Close DR-010 printing + DR-011 mapped drive decisions | APM Digital Ops - Michael Barker | Twiki - Shaun Struik | - | 2026-07-13 | 2026-07-24 | 10 | 0% | Not started |  | - | Task | [18 empty] | 2026-07-13 | 11
S3 | 2 Standard User | Document & design | Finalise DDD V1.0 + CAB | Twiki - Shaun Struik | APM - Samit Chandra | S1,S2 | 2026-07-27 | 2026-07-31 | 5 | 0% | Not started | 2026-07-24 | OK | Task | [18 empty] | 2026-07-27 | 4
S4 | 2 Standard User | Document & design | MILESTONE: Standard User DDD approved | APM - Samit Chandra | APM - Murray Thomas | S3 | 2026-07-31 | 2026-07-31 |  | 0% | Not started | 2026-07-31 | OK | Milestone | [18 empty] | 2026-07-31 | 1
S5 | 2 Standard User | Build | Entra groups (corp/BYOD/hosts) + CA (block unmanaged, allow Windows App, context groups) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N11,S4 | 2026-08-03 | 2026-08-12 | 8 | 0% | Not started | 2026-07-31 | OK | Task | [18 empty] | 2026-08-03 | 9
S6 | 2 Standard User | Build | Azure Files Premium FSLogix + Entra Kerberos | Twiki - Shaun Struik | Twiki - Michael Webster | N11 | 2026-08-03 | 2026-08-12 | 8 | 0% | Not started | 2026-07-17 | OK | Task | [18 empty] | 2026-08-03 | 9
S7 | 2 Standard User | Build | Compute Gallery + golden image (multi-session, M365, Teams optimised) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S6 | 2026-08-12 | 2026-08-21 | 8 | 0% | Not started | 2026-08-12 | OK | Task | [18 empty] | 2026-08-12 | 9
S8 | 2 Standard User | Build | Nerdio pooled host pool + corp/BYOD app groups + autoscale | Twiki - Shaun Struik | Nerdio | S7 | 2026-08-21 | 2026-08-26 | 4 | 0% | Not started | 2026-08-21 | OK | Task | [18 empty] | 2026-08-21 | 5
S9 | 2 Standard User | Build | Scope 14 Intune policies + AVD profiles to session hosts | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S7 | 2026-08-21 | 2026-08-26 | 4 | 0% | Not started | 2026-08-21 | OK | Task | [18 empty] | 2026-08-21 | 5
S10 | 2 Standard User | Pilot & rollout | Pilot 25-50 users (mixed personas) | Twiki - Shaun Struik | APM EUC - Nick Dorbie | S8,S9 | 2026-08-26 | 2026-09-04 | 8 | 0% | Not started | 2026-08-26 | OK | Task | [18 empty] | 2026-08-26 | 9
S11 | 2 Standard User | Pilot & rollout | Validate CA from corporate + personal device | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | S5,S10 | 2026-08-26 | 2026-08-29 | 3 | 0% | Not started | 2026-09-04 | Overlap | Task | [18 empty] | 2026-08-26 | 3
S12 | 2 Standard User | Pilot & rollout | Production rollout (entitle staff, comms, Windows App self-serve) | APM EUC - Nick Dorbie | APM - Kath Nash | S10 | 2026-09-07 | 2026-09-25 | 15 | 0% | Not started | 2026-09-04 | OK | Task | [18 empty] | 2026-09-07 | 18
S13 | 2 Standard User | Pilot & rollout | MILESTONE: Standard User AVD GA | APM EUC - Nick Dorbie | APM - Murray Thomas | S12 | 2026-09-25 | 2026-09-25 |  | 0% | Not started | 2026-09-25 | OK | Milestone | [18 empty] | 2026-09-25 | 1
E1 | 3 ES | Design adaptation | Adapt JS image: midnight daily reset (vs 10-min inactivity) | Twiki - Shaun Struik | APM ES - Ben Riches | J8 | 2026-07-27 | 2026-07-31 | 5 | 0% | Not started | 2026-07-24 | OK | Task | [18 empty] | 2026-07-27 | 4
E2 | 3 ES | Design adaptation | Redesign take-home: any Wi-Fi, off-site filtering (Zscaler client on device), revised CA | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | E1 | 2026-08-03 | 2026-08-14 | 10 | 0% | Not started | 2026-07-31 | OK | Task | Y | [17 empty] | 2026-08-03 | 11
E3 | 3 ES | Design adaptation | ES DDD + CAB | Twiki - Shaun Struik | APM - Samit Chandra | E2 | 2026-08-17 | 2026-08-21 | 5 | 0% | Not started | 2026-08-14 | OK | Task | [18 empty] | 2026-08-17 | 4
E4 | 3 ES | Design adaptation | MILESTONE: ES DDD approved | APM - Samit Chandra | APM - Murray Thomas | E3 | 2026-08-21 | 2026-08-21 |  | 0% | Not started | 2026-08-21 | OK | Milestone | [18 empty] | 2026-08-21 | 1
E5 | 3 ES | Build & test | Build ES image/profiles (midnight reset, incl. Eskilled folder) | Twiki - Shaun Struik | APM ES - Claire McArdle | E4 | 2026-08-24 | 2026-09-02 | 8 | 0% | Not started | 2026-08-21 | OK | Task | [18 empty] | 2026-08-24 | 9
E6 | 3 ES | Build & test | Test off-site scenarios (home Wi-Fi, reset, filtering) | Twiki - Shaun + Dave | APM ES - Ben Riches | E5 | 2026-09-02 | 2026-09-07 | 4 | 0% | Not started | 2026-09-02 | OK | Task | Y | [17 empty] | 2026-09-02 | 5
E7 | 3 ES | Rollout | Pilot + rollout (take-home devices) | Twiki - Dave Badger | APM ES - Ben Riches | E6 | 2026-09-08 | 2026-09-18 | 9 | 0% | Not started | 2026-09-07 | OK | Task | [18 empty] | 2026-09-08 | 10
E8 | 3 ES | Rollout | MILESTONE: ES live | Twiki - Dave Badger | APM - Murray Thomas | E7 | 2026-09-18 | 2026-09-18 |  | 0% | Not started | 2026-09-18 | OK | Milestone | [18 empty] | 2026-09-18 | 1
P1 | 4 Privileged | Design | Privileged design: PAW-style hardened image (no mail/Teams/browse), two tiers Priv(zz)/High-Priv(xy) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | N11 | 2026-08-10 | 2026-08-21 | 10 | 0% | Not started | 2026-07-17 | OK | Task | Y | [17 empty] | 2026-08-10 | 11
P2 | 4 Privileged | Design | Production access model: PIM per tier, just-in-time elevation, approval + audit | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P1 | 2026-08-17 | 2026-08-26 | 8 | 0% | Not started | 2026-08-21 | Overlap | Task | [18 empty] | 2026-08-17 | 9
P3 | 4 Privileged | Design | Privileged Access DDD + CAB | Twiki - Shaun Struik | APM - Samit Chandra | P2 | 2026-08-24 | 2026-08-28 | 5 | 0% | Not started | 2026-08-26 | Overlap | Task | [18 empty] | 2026-08-24 | 4
P4 | 4 Privileged | Design | MILESTONE: Privileged DDD approved | APM - Samit Chandra | APM - Jensen Spencer | P3 | 2026-08-28 | 2026-08-28 |  | 0% | Not started | 2026-08-28 | OK | Milestone | [18 empty] | 2026-08-28 | 1
P5 | 4 Privileged | YubiKey | Test YubiKey 5C NFC FIPS (phishing-resistant MFA for zz/xy) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P1 | 2026-08-17 | 2026-08-26 | 8 | 0% | Not started | 2026-08-21 | Overlap | Task | Y | [17 empty] | 2026-08-17 | 9
P6 | 4 Privileged | YubiKey | MILESTONE: YubiKey 5C NFC FIPS validated | APM Cyber - Ugbaad Adani | Twiki - Shaun Struik | P5 | 2026-08-26 | 2026-08-26 |  | 0% | Not started | 2026-08-26 | OK | Milestone | Y | [17 empty] | 2026-08-26 | 1
P7 | 4 Privileged | Build | Build hardened Privileged image + secure pool | Twiki - Shaun Struik | Twiki - Michael Webster | P4 | 2026-08-31 | 2026-09-09 | 8 | 0% | Not started | 2026-08-28 | OK | Task | Y | [17 empty] | 2026-08-31 | 9
P8 | 4 Privileged | Build | CA + PIM for Priv(zz) & High-Priv(xy) production scopes; YubiKey-only sign-in | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P6,P7 | 2026-09-09 | 2026-09-16 | 6 | 0% | Not started | 2026-09-09 | OK | Task | Y | [17 empty] | 2026-09-09 | 7
P9 | 4 Privileged | Pilot & cutover | Pilot privileged users (both tiers) + validate prod access via YubiKey | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | P8 | 2026-09-16 | 2026-09-23 | 6 | 0% | Not started | 2026-09-16 | OK | Task | [18 empty] | 2026-09-16 | 7
P10 | 4 Privileged | Pilot & cutover | MILESTONE: Privileged Access live (zz + xy) | Twiki - Shaun Struik | APM - Jensen Spencer | P9 | 2026-09-23 | 2026-09-23 |  | 0% | Not started | 2026-09-23 | OK | Milestone | Y | [17 empty] | 2026-09-23 | 1
D1 | 5 Developer | Design | Finalise Dev DDD: permissive dev image, limited blocks, no production-access path | Twiki - Shaun Struik | APM - Samit Chandra | N11 | 2026-08-24 | 2026-09-02 | 8 | 0% | Not started | 2026-07-17 | OK | Task | [18 empty] | 2026-08-24 | 9
D2 | 5 Developer | Design | Design Dev network from JS pattern + adjust (deny-by-default egress, Zscaler at endpoint) | Twiki - Shaun Struik | APM Network - Michael Court | N11 | 2026-08-31 | 2026-09-04 | 5 | 0% | Not started | 2026-07-17 | OK | Task | [18 empty] | 2026-08-31 | 4
D3 | 5 Developer | Build | AVD landing zone (Bicep) + FSLogix Premium ZRS + Sentinel + Entra groups | Twiki - Shaun Struik | Twiki - Michael Webster | D1,D2 | 2026-09-07 | 2026-09-14 | 6 | 0% | Not started | 2026-09-04 | OK | Task | [18 empty] | 2026-09-07 | 7
D4 | 5 Developer | Build | AIB image pipeline (Git template, signing, SBOM) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | D3 | 2026-09-09 | 2026-09-16 | 6 | 0% | Not started | 2026-09-14 | Overlap | Task | [18 empty] | 2026-09-09 | 7
D5 | 5 Developer | Build | Primary pooled host pool + scaling plan (nested virtualisation) | Twiki - Shaun Struik | Nerdio | D4 | 2026-09-14 | 2026-09-18 | 5 | 0% | Not started | 2026-09-16 | Overlap | Task | [18 empty] | 2026-09-14 | 4
D6 | 5 Developer | Build | Dev tooling layers (VS, Podman/containers, WSL2) with limited blocks | Twiki - Shaun Struik | APM EUC - Nick Dorbie | D5 | 2026-09-16 | 2026-09-23 | 6 | 0% | Not started | 2026-09-18 | Overlap | Task | [18 empty] | 2026-09-16 | 7
D7 | 5 Developer | Pilot & GA | Pilot ring (PDE owner + cohort) + smoke test + CA enforced | Twiki - Shaun Struik | APM - PDE owner (TBC) | D5 | 2026-09-21 | 2026-09-25 | 5 | 0% | Not started | 2026-09-18 | OK | Task | [18 empty] | 2026-09-21 | 4
D8 | 5 Developer | Pilot & GA | Team-by-team migration from legacy PDE | Twiki - Shaun Struik | APM EUC - Nick Dorbie | D7 | 2026-09-25 | 2026-10-02 | 6 | 0% | Not started | 2026-09-25 | OK | Task | [18 empty] | 2026-09-25 | 7
D9 | 5 Developer | Pilot & GA | Capability phases 2-3 (winget/ACR; Copilot/MCP/local LLM) | Twiki - Shaun Struik | APM Cyber - Ugbaad Adani | D8 | 2026-09-28 | 2026-10-09 | 10 | 0% | Not started | 2026-10-02 | Overlap | Task | [18 empty] | 2026-09-28 | 11
D10 | 5 Developer | Pilot & GA | Retire legacy PDE after 1 month stable | Twiki - Shaun Struik | APM Digital Ops - Michael Barker | D8 | 2026-10-09 | 2026-10-16 | 6 | 0% | Not started | 2026-10-02 | OK | Task | [18 empty] | 2026-10-09 | 7
D11 | 5 Developer | Pilot & GA | MILESTONE: Developer SOE GA (past 30 Sep on current resourcing) | Twiki - Shaun Struik | APM - Murray Thomas | D8,D9 | 2026-10-09 | 2026-10-09 |  | 0% | Not started | 2026-10-09 | OK | Milestone | Y | [17 empty] | 2026-10-09 | 1
L1 | 6 Logistics | Job Seeker | Retrieve old JS devices onsite + place new (rolling) | Twiki - Dave Badger | APM ES - Ben Riches | J12 | 2026-08-11 | 2026-09-11 | 24 | 0% | Not started | 2026-08-04 | OK | Task | [18 empty] | 2026-08-11 | 31
L2 | 6 Logistics | All | Asset register updates (ongoing) | Twiki - Dave Badger | APM EUC - Nick Dorbie | - | 2026-08-04 | 2026-09-30 | 42 | 0% | Not started |  | - | Task | [18 empty] | 2026-08-04 | 57
L3 | 6 Logistics | Standard User | Retrieve standard-user laptops as AVD replaces | Twiki - Dave Badger | APM EUC - Nick Dorbie | S13 | 2026-09-07 | 2026-09-30 | 18 | 0% | Not started | 2026-09-25 | Overlap | Task | [18 empty] | 2026-09-07 | 23
L4 | 6 Logistics | Privileged | Retrieve/contract high-priv laptops to users on own Macs (via Privileged image) | Twiki - Dave Badger | APM - Murray Thomas | P10 | 2026-09-23 | 2026-09-30 | 6 | 0% | Not started | 2026-09-23 | OK | Task | [18 empty] | 2026-09-23 | 7
K1 | 7 KB & Enablement | Network | KB: APM-KIOSK build/cutover + Azure hub-spoke pattern | Twiki - Shaun (build) | Kath Nash -> Michael Court | N10 | 2026-07-13 | 2026-07-20 | 6 | 0% | Not started | 2026-07-15 | Overlap | Task | [18 empty] | 2026-07-13 | 7
K2 | 7 KB & Enablement | Job Seeker | KB: CompNow wipe/prep/ship process | Twiki - Shaun (build) | Kath Nash -> CompNow | J9 | 2026-07-24 | 2026-07-29 | 4 | 0% | Not started | 2026-07-29 | Overlap | Task | [18 empty] | 2026-07-24 | 5
K3 | 7 KB & Enablement | Job Seeker | KB: JS ops (password rotation, lock screen, site cutover, device replace) | Twiki - Shaun (build) | Kath Nash -> Nick Dorbie / Rohit Singh | J5 | 2026-07-27 | 2026-08-10 | 11 | 0% | Not started | 2026-07-20 | OK | Task | [18 empty] | 2026-07-27 | 14
K4 | 7 KB & Enablement | Standard User | KB: image/patch, FSLogix lifecycle, CA BYOD, Windows App onboarding | Twiki - Shaun (build) | Kath Nash -> Nick Dorbie | S8 | 2026-08-26 | 2026-09-07 | 9 | 0% | Not started | 2026-08-26 | OK | Task | [18 empty] | 2026-08-26 | 12
K5 | 7 KB & Enablement | ES | KB: ES midnight reset, off-site connectivity, Eskilled access | Twiki - Shaun (build) | Kath Nash -> Ben Riches / Rohit Singh | E5 | 2026-08-24 | 2026-09-02 | 8 | 0% | Not started | 2026-09-02 | Overlap | Task | [18 empty] | 2026-08-24 | 9
K6 | 7 KB & Enablement | Privileged | KB: Privileged access request, PIM per tier (zz/xy), YubiKey enrolment | Twiki - Shaun (build) | Kath Nash -> Ugbaad Adani / Rohit Singh | P7 | 2026-09-09 | 2026-09-18 | 8 | 0% | Not started | 2026-09-09 | OK | Task | [18 empty] | 2026-09-09 | 9
K7 | 7 KB & Enablement | Developer | KB: Dev image pipeline/rollback, self-service tooling, MCP request, FSLogix recovery | Twiki - Shaun (build) | Kath Nash -> PDE owner / Rohit Singh | D6 | 2026-09-23 | 2026-10-02 | 8 | 0% | Not started | 2026-09-23 | OK | Task | [18 empty] | 2026-09-23 | 9
K8 | 7 KB & Enablement | Service Desk | KB: Tier-1 Service Desk triage runbooks (all use cases) | Twiki - Shaun (build) | Kath Nash -> Rohit Singh | K3 | 2026-09-14 | 2026-09-30 | 13 | 0% | Not started | 2026-08-10 | OK | Task | [18 empty] | 2026-09-14 | 16

## Gantt Chart
Native Gantt (bars). Edit dates on Program Plan and this updates. Coloured by workstream, gold milestones, red critical. Bars past 30 Sep show Developer spill.

## Stakeholders & RACI
Stakeholders & RACI
Name | Org | Role | Accountable / Owns | Reports to
Murray Thomas | APM | Digital Delivery Portfolio Manager | This project - decision authority & escalation. Shaun + Dave report here. | -
Nathan Heaton | APM | Program Manager (overall) | Program-level coordination across projects | -
Samit Chandra | APM | Head of Digital Transformation & Architecture | DDD owner; architecture authority; Dev requirements sign-off | -
Jensen Spencer | APM | CTO / CISO | All Cyber and IT; Privileged Access authority; approved JS printing | -
Michael Barker | APM | Head of Digital Operations | Operations; SSID approval; Dev support model; PDE decommission | Jensen Spencer
Michael Court | APM | IT Infrastructure Lead | Network & infrastructure build (site + Azure) | Jensen Spencer (assumed)
Ugbaad Adani | APM | Cyber Security | Cyber controls, RFFR assurance, CA/PIM, Privileged Access + YubiKey | Jensen Spencer (assumed)
Nick Dorbie | APM | End User Compute Manager | EUC build/operations, Intune | Michael Barker (assumed)
Rohit Singh | APM | IT Service Lead / Service Desk | Support, triage runbooks | Michael Barker (assumed)
Kath Nash | APM | Digital Business Partner | All instructions + comms; KB validation | Michael Barker (assumed)
Ben Riches | APM | ES Lead | Business owner: Job Seeker, ES (take-home), ES devices | -
James Muller | APM | CEO Employment Services | Executive sponsor | -
Claire McArdle | APM | ES (Eskilled) | ES Eskilled training content | -
PDE owner | APM | To be nominated | Developer platform owner (Dev service catalogue, image approval) | Michael Barker (assumed)
Michael Webster | Twiki Corp | Architecture Lead (Azure, Cloud, Security) | Solution architecture | Samit Chandra
Shaun Struik | Twiki Corp | Solution Engineer AVD | AVD build & delivery; KB authoring | Murray Thomas
David Badger | Twiki Corp | Project Manager | PM + device logistics / retrieval | Murray Thomas
CompNow | External | Device partner | Device wipe/prep/build/ship | -
Nerdio | External | AVD orchestration platform | Host pool management, autoscale, reimaging | -

## KB Register
KB Register - build by Shaun, validate by Kath Nash, then validate by process stakeholder (APM KB standard, admin review before publish)
KB ID | Workstream | Process / KB Title | Built by | Validate 1 | Validate 2 (stakeholder) | Owning team | Status
KB-N1 | 0 Network | APM-KIOSK site network build & site cutover | Shaun Struik | Kath Nash | Michael Court | Network | Not started
KB-N2 | 0 Network | Azure hub-spoke reusable build pattern | Shaun Struik | Kath Nash | Michael Webster | Cloud / Azure | Not started
KB-J1 | 1 Job Seeker | CompNow device wipe / prep / Autopilot / label / ship | Shaun Struik | Kath Nash | CompNow + Nick Dorbie | EUC / Vendor | Not started
KB-J2 | 1 Job Seeker | Kiosk password rotation runbook (Azure Automation) | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Not started
KB-J3 | 1 Job Seeker | Lock screen proactive remediation | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-J4 | 1 Job Seeker | F3 account create / retire runbook | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Not started
KB-J5 | 1 Job Seeker | Site VLAN to APM-KIOSK cutover (per site) | Shaun Struik | Kath Nash | Michael Court | Network | Not started
KB-J6 | 1 Job Seeker | Kiosk device replacement / RMA | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started
KB-S1 | 2 Standard User | Golden image build & monthly patch (Nerdio) | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-S2 | 2 Standard User | FSLogix profile lifecycle (create/snapshot/restore/deprovision) | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-S3 | 2 Standard User | CA BYOD vs corporate troubleshooting | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber | Not started
KB-S4 | 2 Standard User | Windows App onboarding (corporate + BYOD) | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started
KB-S5 | 2 Standard User | Host pool scaling / capacity management | Shaun Struik | Kath Nash | Nick Dorbie | EUC | Not started
KB-E1 | 3 ES | ES midnight reset operation | Shaun Struik | Kath Nash | Ben Riches | ES | Not started
KB-E2 | 3 ES | ES off-site connectivity (any Wi-Fi) + filtering | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started
KB-E3 | 3 ES | Eskilled access (ES) | Shaun Struik | Kath Nash | Claire McArdle | ES | Not started
KB-P1 | 4 Privileged | Privileged Access request & approval (Priv zz / High-Priv xy) | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P2 | 4 Privileged | PIM elevation per tier (production access) | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P3 | 4 Privileged | YubiKey 5C NFC FIPS enrolment | Shaun Struik | Kath Nash | Ugbaad Adani | Cyber / Identity | Not started
KB-P4 | 4 Privileged | Privileged image build & hardening | Shaun Struik | Kath Nash | Michael Webster | Cloud / Cyber | Not started
KB-D1 | 5 Developer | AIB image pipeline + rollback | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D2 | 5 Developer | Dev self-service tooling (winget / Company Portal) | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D3 | 5 Developer | MCP server request / allowlist | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D4 | 5 Developer | OIDC deployment pipeline request | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-D5 | 5 Developer | FSLogix profile recovery (Dev) | Shaun Struik | Kath Nash | PDE owner (TBC) | Platform | Not started
KB-SD1 | 7 KB & Enablement | Tier-1 Service Desk triage runbooks (all use cases) | Shaun Struik | Kath Nash | Rohit Singh | Service Desk | Not started

## Assumptions & Risks
Assumptions, Risks & Open Decisions
# | Risk / Assumption / Open decision | Impact | Likelihood | Owner | Mitigation / Recommendation
1 | Five AVD use cases + national device rollout in 14 weeks, with Shaun as the single build engineer, does not fit. Developer is now last and its GA lands in mid-October, past the 30 Sep contract end. | High | High | Murray Thomas / Twiki | Commit Network + Job Seeker + Standard User + ES. Treat Privileged and Developer as stretch. Add a second engineer, or scope Developer to design + pilot only by 30 Sep with GA after.
2 | Network skills gap caused the 30 Jun miss. Network is on the critical path from day one. | High | Med | Michael Court / Michael Webster | Twiki leads Azure foundation. Confirm APM Network resourcing for the site build this week. Daily stand-up until network is proven.
3 | Privileged Access is a net-new design (PAW-style, two tiers zz/xy, YubiKey) added mid-window. It carries the production-access blast-radius risk. | High | Med | Shaun / Ugbaad / Jensen Spencer | Design once, gate hard on YubiKey. Jensen Spencer signs off the privileged model. Do not cut over high-priv until P6 (YubiKey validated) and P8 (CA/PIM) pass.
4 | YubiKey 5C NFC FIPS now gates Privileged production access for zz/xy. If it fails, no phishing-resistant path to production from Macs. | High | Med | Shaun / Ugbaad Adani | Run the YubiKey test early (week of 17 Aug). Fallback to a dedicated hardened Cloud PC for the highest tier if FIPS keys do not validate.
5 | ES take-home (was CTA) breaks the site-VLAN / PSK / site-Zscaler controls Job Seeker relies on. It is a security redesign, now 3rd in order. | High | High | Shaun / Ugbaad Adani | Treat ES as its own design (Zscaler client on device, revised CA, any Wi-Fi, midnight reset). Confirm Eskilled access path with Claire McArdle.
6 | Developer is a separate permissive image (limited blocks, no production path). Production access lives only in the Privileged image. | Med | Low | Shaun / Samit Chandra | Keep the boundary clean: no production scopes on the Dev pool. Samit Chandra signs off Dev requirements.
7 | Standard User printing (DR-010) and mapped drive (DR-011) still pending. Both gate the SU build. | Med | High | Michael Barker / Nick Dorbie | Force decisions by 24 Jul. Universal Print is the likely path. Confirm mapped-drive backend (SharePoint / Azure Files / on-prem).
8 | Job Seeker device count inconsistent across the DDD (517 vs 540). | Med | High | Dave Badger / Nick Dorbie | Reconcile against SoftwareOne licensing (540) and the site allocation list before procurement and rollout.
9 | Nerdio assumed already deployed and operational. Standard User, ES and Developer all reuse it. | High | Low | Shaun / Michael Webster | Confirm Nerdio is live in the tenant. If not, add a deployment task that gates the Job Seeker AVD build.
10 | Developer PDE owner not yet named. Gates Dev pilot, image approval and the Dev service catalogue. | Med | Med | Murray Thomas / Michael Barker | Nominate the APM PDE owner now so Dev pilot and KB validation have an APM stakeholder.
11 | Contract ends 30 Sep. Privileged lands on the final week and Developer past it, with no buffer. | High | High | Murray Thomas | Agree what 'done by 30 Sep' means per use case: live, piloted, or designed. Privileged live by 30 Sep is achievable only if it is protected from descoping.